## CONTINUATION_CONTEXT
PUP MANET PROJECT — CONTINUATION CONTEXT
PROJECT STATUS | Android Steps 001–017 completed successfully.
LATEST COMPLETED STEP | STEP 017 — ESP32 Firmware Packet Parser
NEXT STEP | STEP 018 — ESP32 Bluetooth Service
CURRENT GIT BRANCH | step-002-003-esp32-simulation
ANDROID STATUS | Android app builds and runs in Android Studio emulator/device.
ANDROID FEATURES | Adaptive routing, failover simulation, packet abstraction, queue engine, diagnostics, Bluetooth simulation layer, validation checklist, protocol preview, readiness checklist.
ESP32 STATUS | ESP32 parser implemented in esp32-node-platformio. No live Bluetooth or LoRa transport yet.
OFFICIAL SYSTEM ARCHITECTURE | Android Phone ↔ Bluetooth ↔ ESP32 ↔ LoRa ↔ ESP32 ↔ Bluetooth ↔ Android Phone
IMPORTANT DESIGN RULE | USB Serial removed from Android scope. Bluetooth is the official Android-to-ESP32 transport.
REAL HARDWARE STATUS | Still simulation-first. Real Bluetooth integration has not yet started.
LATEST TAGS | android-step-009 through android-step-016, step-017-esp32-packet-parser
WORKFLOW RULE | Always continue from NEXT incomplete step only. Do not restart the project.
CONTINUATION INSTRUCTION | If this workbook is attached in a future chat, the AI should study this workbook first and continue from the next incomplete step.
NEXT IMPLEMENTATION ROADMAP | 018 ESP32 Bluetooth Service → 019 Android Bluetooth Permissions → 020 Android Bluetooth Socket Layer → 021 Android↔ESP32 Live Packet Test → 022 ESP32↔ESP32 LoRa Live Test

## Dashboard
PUP MANET Emergency Messaging - Codex/GitHub Tracker
Current Workflow | Android app first, then return to ESP32 LoRa/RPi gateway | Priority | Area | Status | Evidence Needed | Notes
Current Active Step | A1 - Android app skeleton and simulation UI | 1 | Android app skeleton | Next | Gradle build / screenshot | Use simulation first
Last Completed | Step 002/003 ESP32 simulation compiled, uploaded, and serial monitor partially validated | 2 | Android chat UI | Planned | Emulator/device screenshot | Manual network selection
Reason for Pivot | User wants to build Android messaging app first while preserving where ESP32 work stopped | 3 | Android local simulation engine | Planned | Message sent/queued/delivered logs | No hardware required
Source of Truth | This workbook + GitHub repo | 4 | Bluetooth placeholder/service | Planned | Permission screen + mock status | Real BLE/SPP later
GitHub Repo | pagibetech/pup-manet-emergency-messaging | 5 | Return to ESP32 | Paused | STATUS/NEIGHBORS parser test | Resume after Android baseline
Workbook Rule | Update after every merged Codex task and every local test result | 6 | LoRa hardware | Deferred | Two ESP32 LoRa packet exchange | After app baseline
Next After Android | Return to ESP32 command parser validation, then LoRa hardware layer | 7 | RPi gateway | Deferred | Gateway simulator logs | After ESP32/Android baseline

## README
PUP MANET Emergency Messaging Workbook
Primary development workflow | Codex Web + GitHub pull requests. VS Code is optional and no longer required for the main workflow.
Local development workflow | Codex CLI on MacBook Pro M1 Max for local review, repo edits, build checks, and troubleshooting.
Repository source of truth | GitHub repository: pup-manet-emergency-messaging
Workbook source of truth | This workbook remains the project tracker. It must be updated after each completed Codex task and hardware validation step.
Development order | ESP32 PlatformIO simulation -> ESP32 LoRa/Bluetooth -> Raspberry Pi gateway simulation -> Raspberry Pi LoRa/WiFi router link -> Android messaging app -> integrated testing.
Test priority | All implementation must satisfy DOCX test procedures first: baseline, degradation detection, failover, sustained operation, and recovery.
Hardware testing note | Codex can create and test code logic, but physical LoRa, Bluetooth, WiFi router, and GSM validation must be performed by the user and recorded in this workbook.
Update date | 2026-05-05
Current workflow decision | Proceed with Codex-only workflow: Codex Web as primary, Codex CLI as secondary/local, GitHub as code storage, workbook as status control.
LATEST STATUS UPDATE
Android Steps 001-012 completed and validated.
GitHub repository synchronized and merged into main branch.
Current Android app includes adaptive routing, failover simulation, queue engine, diagnostics, validation checklist, and tabbed field UI.
Next recommended phase: Android Step 013 real transport abstraction and hardware bridge preparation.

## Architecture
PUP MANET Test-Aligned Architecture Summary
Item | Updated Test-Aligned Decision | Reason / Acceptance Link | Status | Owner | Evidence | Date Completed | Notes
Primary validated path | Android App → Bluetooth → ESP32 LoRa Node → LoRa MANET → Raspberry Pi Gateway → WiFi-router simulated satellite → Remote Gateway → LoRa MANET → Bluetooth → Android App | Directly exercises baseline, failover, store-forward, recovery, and end-to-end delivery tests. | Approved for Phase 1
Node pairing | Each MANET node is paired to one Android phone over Bluetooth. | Ensures Android messaging app can still inject messages to LoRa when WiFi/GSM are unavailable. | Approved
Manual network selection | Android app shall support Auto, LoRa, WiFi, and GSM selection. | Extra feature allowed but must not interfere with DOCX validation path. | Approved
Auto mode behavior | Auto mode checks WiFi, GSM, and Bluetooth/LoRa availability, then selects best available route. | Allows failover decisions while preserving manual test control. | Approved
Failover trigger | RSSI below -78 dBm for 10 seconds OR route/ACK timeout triggers failover to simulated satellite path. | Matches network degradation and failover activation procedures. | Approved
Recovery trigger | Primary MANET route stable for 10 seconds triggers return to MANET; target switchback ≤5 seconds. | Matches recovery/reversion test procedure. | Approved
Message not found locally
Simulation first | All code shall include simulation mode before physical LoRa validation.
Development Order | Simulation → ESP32 PlatformIO code → Raspberry Pi gateway code → Android chat app.

## Phase Plan
STAGED IMPLEMENTATION PLAN — CODEX + GITHUB WORKFLOW
Phase | Name | Goal | Primary Output | Entry Criteria | Exit Criteria | Main Tools | Status | Notes
0 | Project Baseline | Finalize architecture and workbook | Approved workbook and topology | User confirms direction | Workbook ready and first active step chosen | Excel/ChatGPT | In Progress | This workbook is the continuity reference.
0.5 | GitHub + Codex Setup | Move development workflow into GitHub with Codex task control | Repository, AGENTS.md, README, workbook in docs/ | Workbook baseline available | Repo can be opened by VS Code/Codex and pushed to GitHub | GitHub, VS Code, Codex CLI/Cloud | Not Started | Added because user will develop using Codex on MacBook Pro M1 Max.
1 | Simulation Core | Simulate 6 nodes and 2 gateways before hardware | Python simulator with routing/failover logs | GitHub/Codex setup done | Message routing between Network A and B simulated | VS Code, Codex, Python | Not Started | No hardware needed yet.
2 | ESP32 Simulation Firmware | Start PlatformIO ESP32 code in simulation mode | Buildable PlatformIO project | Repo ready and packet format draft ready | Node simulation builds and logs message state | VS Code, PlatformIO, Codex | Not Started | Codex task C1.
3 | ESP32 LoRa Firmware | Add SX1278 Ra-02 LoRa messaging | Firmware for LoRa send/receive and ACK | ESP32 simulation stable | Physical node-to-node message send/ACK works | ESP32, PlatformIO, Codex | Not Started | Start with 2 nodes, then 6.
4 | Raspberry Pi Gateway | Build gateway service and dashboard | Python service + Flask dashboard | Protocol stable | Gateway sends/receives LoRa and routes to WiFi path | Raspberry Pi 3B, Python, Codex | Not Started | Direct LoRa module on Pi.
5 | Router/Satellite Simulation | Connect gateways over WiFi routers | Inter-network messaging with latency simulation | Gateway API stable | Network A can deliver to Network B through WiFi path | Routers, Linux tc/netem | Not Started | Use 500-700 ms delay.
6 | Failover/Recovery Test Logic | Implement and validate DOCX acceptance logic | State machine and test reports | Simulation and gateway stable | Pass baseline, degradation, failover, recovery tests | Codex, Python, PlatformIO | Not Started | RSSI < -78 dBm for 10s and stable 10s recovery.
7 | Android Chat App | Create Android messaging app | Android Studio project | Gateway/ESP32 protocol stable | App sends/receives via selected transport | Android Studio, Kotlin, Codex | Not Started | Manual Auto/LoRa/WiFi/GSM mode selection.
8 | Integrated Test Campaign | Validate acceptance criteria | Signed test results and logs | All components working | PDR, failover, recovery, uptime targets measured | Workbook + logs | Not Started | Update workbook after every passed step.
Codex-Only Development Overlay
Order | Phase | Primary tool | Secondary tool | Requires hardware | Repo area | Completion evidence | Workbook sheet to update | Status
1 | GitHub baseline | Codex Web | Codex CLI | FALSE | repo root + docs | Repo created and initial commit pushed | Codex GitHub Workflow / Repo Structure | Next
2 | ESP32 simulation | Codex Web | Codex CLI | FALSE | esp32-node-platformio | PlatformIO build log | Detailed Steps / Progress Tracker | Planned
3 | RPi gateway simulation | Codex Web | Codex CLI | FALSE | rpi-gateway | pytest/simulation log | Simulation Plan / Progress Tracker | Planned
4 | ESP32 LoRa + Bluetooth | Codex Web | Codex CLI | TRUE | esp32-node-platformio | Hardware test screenshots/logs | Config Tracker / Issue Log | Planned
5 | Gateway LoRa + WiFi routers | Codex Web | Codex CLI | TRUE | rpi-gateway | Inter-gateway routing test | Test Campaign / Progress Tracker | Planned
6 | Android app | Codex Web | Codex CLI + Android Studio | TRUE | android-chat-app | Build/app screenshots | Android App Plan / Progress Tracker | Planned

## Detailed Steps
DETAILED STEP TRACKER - UPDATE AFTER EVERY COMPLETED STEP
Step ID | Phase | Stage | Action / Procedure | Validation / Expected Result | Status | Owner | Date Started | Date Completed | Actual Result | Evidence / File / Screenshot | Notes
0.1 | 0 Baseline | Workbook | Review workbook sheets and confirm architecture | Architecture accepted or edits listed | In Progress | User + ChatGPT
0.2 | 0 Baseline | Topology | Confirm 6-node topology: Network A has 3 nodes, Network B has 3 nodes, each paired by Bluetooth to Android phone, with one gateway and one WiFi router per network | Topology confirmed | Not Started | User + ChatGPT
0.3 | 0 Baseline | Frequency | Confirm prototype frequency and power setting for SX1278 Ra-02 433 MHz | Selected LoRa settings documented | Not Started | User
0.4 | 0.5 GitHub/Codex | Repository | Create GitHub repository pup-manet-emergency-messaging | Repo exists and is accessible | Completed | User |  | 2026-05-11 | GitHub repository created and operational | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
0.5 | 0.5 GitHub/Codex | Local Clone | Clone repo on MacBook Pro M1 Max and open in VS Code | Repo opens locally; git status clean | Completed | User |  | 2026-05-11 | Repository cloned successfully on MacBook Pro M1 Max | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
0.6 | 0.5 GitHub/Codex | Repo Structure | Create required folders: esp32-node-platformio, rpi-gateway, android-chat-app, docs/workbook, docs/diagrams, docs/test-procedures, docs/codex-prompts | Folders exist | Completed | User + Codex |  | 2026-05-11 | Repository structure created and validated | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
0.7 | 0.5 GitHub/Codex | AGENTS.md | Add repository AGENTS.md with project rules for Codex | Codex instructions file exists | Completed | Codex/User |  | 2026-05-11 | AGENTS.md and Codex workflow established | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
0.8 | 0.5 GitHub/Codex | Workbook Commit | Copy latest workbook and diagrams into docs folder and commit to GitHub | Workbook and diagrams are versioned | Completed | User |  | 2026-05-11 | Workbook and diagrams committed to repository | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
0.9 | 0.5 GitHub/Codex | Codex Test Task | Run small Codex task to update README only | Codex completes task without touching unrelated files | Completed | User + Codex |  | 2026-05-11 | Codex workflow validated successfully | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
1.1 | 1 Simulation | Packet Model | Create JSON packet model for message, ACK, HELLO, route advert, gateway advert | Simulator accepts packet schema | Completed | Codex |  | 2026-05-11 | Packet abstraction and schema implemented | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
1.2 | 1 Simulation | Six Nodes | Simulate six nodes: A1-A3 and B1-B3 with two gateways GWA/GWB | All simulated nodes appear in log | Completed | Codex |  | 2026-05-11 | Six-node MANET simulation operational | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
1.3 | 1 Simulation | Local Delivery | Send message from A1 to A2 and A3 through simulated local routing | Message delivered with ACK | Completed | Codex/User |  | 2026-05-11 | Local delivery simulation validated | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
1.4 | 1 Simulation | Cross Network Delivery | Send message from A1 to B1 via Gateway A -> WiFi router link -> Gateway B | Message reaches remote network with ordered delivery | Completed | Codex/User |  | 2026-05-11 | Cross-network routing simulation validated | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
1.5 | 1 Simulation | Degradation Detection | Simulate RSSI below -78 dBm for 10 seconds | System changes to degraded/failover state | Completed | Codex/User |  | 2026-05-11 | Dynamic degradation detection implemented | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
1.6 | 1 Simulation | Recovery Detection | Simulate stable MANET link for 10 seconds and return to MANET within 5 seconds | Recovery succeeds with no message loss | Completed | Codex/User |  | 2026-05-11 | Recovery/failover logic implemented | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
2.1 | 2 ESP32 Sim | PlatformIO Project | Create ESP32 PlatformIO project in simulation mode | pio run succeeds | Completed | Codex |  | 2026-05-11 | ESP32 simulation PlatformIO project operational | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
2.2 | 2 ESP32 Sim | Serial Debug | Print node ID, mode, queue status, and simulated link state to Serial Monitor | Readable serial output | Completed | Codex/User |  | 2026-05-11 | Serial debug and routing diagnostics operational | GitHub commits, Android emulator screenshots, Codex logs | Validated on Android emulator and GitHub repository
3.1 | 3 ESP32 LoRa | LoRa Wiring Doc | Document ESP32-to-SX1278 Ra-02 wiring and pin configuration | Wiring sheet/config updated | Not Started | Codex/User |  |  |  | Wiring doc
3.2 | 3 ESP32 LoRa | LoRa Send/Receive | Implement LoRa packet send/receive | Two nodes exchange packets | Not Started | Codex/User |  |  |  | Serial logs
3.3 | 3 ESP32 LoRa | ACK/Retry | Implement ACK, retry, duplicate filter | Message delivery improves under packet loss | Not Started | Codex/User |  |  |  | Serial logs
4.1 | 4 Gateway | Gateway Simulation | Create Python/Flask gateway simulation service | Runs on Mac/RPi in simulation mode | Not Started | Codex |  |  |  | Dashboard screenshot | Use Codex task C3.
4.2 | 4 Gateway | LoRa SPI Integration | Connect Raspberry Pi 3B directly to LoRa module via SPI through hardware abstraction layer | Gateway receives node heartbeats | Not Started | Codex/User |  |  |  | RPi logs
5.1 | 5 Router Link | Router-to-Router Link | Configure/verify two WiFi routers connected wirelessly as simulated satellite path | Gateway A can ping Gateway B through router path | Not Started | User |  |  |  | Ping log
5.2 | 5 Router Link | Latency Simulation | Apply 500-700 ms simulated latency using Linux tc/netem where applicable | Latency measured in logs | Not Started | User/Codex |  |  |  | Ping log
6.1 | 6 Failover | Failover State Machine | Implement RSSI < -78 dBm for 10 seconds and ACK/timeout failover triggers | Failover starts within 10 seconds | Not Started | Codex/User |  |  |  | Test log | Use Codex task C5.
6.2 | 6 Failover | Store and Forward | Buffer messages during failover and preserve order | No message loss during route switch | Not Started | Codex/User |  |  |  | Queue logs
6.3 | 6 Failover | Recovery | Return to MANET after stable link for 10 seconds; complete switch within 5 seconds | Recovery passes acceptance criteria | Not Started | Codex/User |  |  |  | Timestamped logs
7.1 | 7 Android | Android Project | Create Android Studio Kotlin app MVP | Project builds | Not Started | Codex/User |  |  |  | Build screenshot | Use Codex task C6.
7.2 | 7 Android | Bluetooth Pairing | Pair Android phone to assigned ESP32 node via Bluetooth | Phone can send test message to node | Not Started | Codex/User |  |  |  | App screenshot/serial log
7.3 | 7 Android | Network Selection | Add Auto, LoRa, WiFi, GSM manual mode selector | UI and internal state work | Not Started | Codex/User |  |  |  | App screenshot
8.1 | 8 Test Campaign | Baseline Test | Run DOCX baseline operation test | PDR >=95%, MANET forms <30 sec, satellite inactive | Not Started | User |  |  |  | Test report
8.2 | 8 Test Campaign | Degradation Test | Run DOCX degradation detection test | RSSI < -78 dBm for 10 seconds detected | Not Started | User |  |  |  | Test report
8.3 | 8 Test Campaign | Failover Test | Run DOCX failover activation test | Failover trigger time = 10 seconds | Not Started | User |  |  |  | Test report
8.4 | 8 Test Campaign | Sustained Operation | Run 24-hour sustained emergency operation test | Uptime >=80%; no unrecoverable failure | Not Started | User |  |  |  | Test report
8.5 | 8 Test Campaign | Recovery Test | Run DOCX recovery/reversion test | Switch back within 5 seconds with no message loss | Not Started | User |  |  |  | Test report
ANDROID-FIRST PIVOT STEPS - INSERTED 2026-05-10
Step ID | Phase | Stage | Action / Procedure | Validation / Expected Result | Status | Owner | Date Started | Date Completed | Actual Result | Evidence / File / Screenshot | Notes
A1 | Android First | Skeleton | Create Android app skeleton under android-chat-app using Codex | Project exists and opens/builds in Android Studio | Next | Codex + User |  |  |  | Gradle/build screenshot | Do before LoRa hardware
A2 | Android First | Chat UI | Build simulated chat UI | Can compose and show local messages | Planned | Codex + User |  |  |  | App screenshot | Simulation only
A3 | Android First | Route Selection | Add AUTO/WIFI/GSM/LORA manual selector | Selected route visible and saved in UI state | Planned | Codex + User |  |  |  | Screenshot | User requirement
A4 | Android First | Mock Transport | Add mock fallback logic: WiFi/GSM unavailable -> LoRa | Message status changes queued/sent/delivered | Planned | Codex + User |  |  |  | Test log | No real radios
A5 | Android First | Documentation | Update Android README and task logs | New chat can continue from workbook and task logs | Planned | Codex |  |  |  | Task log path | Required before returning to hardware
R1 | Resume ESP32 | Parser Validation | Return to ESP32 Step 003 command parser validation | STATUS, NEIGHBORS, SEND commands behave correctly | Paused | User + ChatGPT |  |  |  | Serial monitor output | Exact return point after Android baseline
R2 | Resume Hardware | LoRa Layer | Proceed to ESP32 SX1278 LoRa hardware integration | Two-node packet exchange works | Deferred | Codex + User |  |  |  | LoRa test log | Requires ESP32/SX1278 wiring details

## Hardware BOM
Hardware Bill of Materials and Notes
Item | Qty | Use | Recommended Spec | Already Available? | Priority | Risk | Validation Test | Status | Notes
ESP32 Dev Board | 6+ | MANET nodes | ESP32 WROOM-32 acceptable; ESP32-S3 optional | Yes/confirm | High | Pin/library differences | Blink + serial + LoRa init | Planned | Use same board type if possible.
SX1278 Ra-02 433 MHz | 8 | 6 nodes + 2 gateways | 433 MHz module with correct antenna | Yes/confirm | High | Regulatory/power limits; bad antenna | LoRa send/receive at short range | Planned | Use low power for prototype.
Raspberry Pi 3B | 2 | Gateways | Pi 3B with stable 5V supply | Confirm | High | SPI wiring, CPU limits | Python LoRa gateway receives packets | Planned | Use Lite OS if possible.
WiFi Router 2.4 GHz | 2 | Satellite simulation | Router that supports wireless bridge/repeater/client mode preferred | Yes | High | May not bridge wirelessly | Gateway ping test | Planned | If unsupported, use OpenWrt/travel router.
Android Phone | 1+ | Chat app testing | Android 8+ recommended | Confirm | Medium | Network permissions/background limits | Install APK, connect to gateway | Future | Start web dashboard first.
Li-ion Battery Pack | 6 | Portable nodes | 3.7V/5V boost or regulated 5V | Confirm | Medium | Voltage sag | Runtime and battery reading test | Future | Simulation first.

## Config Tracker
Configuration Tracker
Parameter | Default / Starting Value | Where Used | Reason | Can Change? | Updated Value | Date Updated | Notes
LoRa Frequency | 433 MHz / PH_433-compatible prototype setting | ESP32 + Pi LoRa | Available SX1278 Ra-02 hardware | Yes |  |  | Verify compliance for non-lab use.
LoRa TX Power | Start low; do not maximize during lab tests | ESP32 + Pi LoRa | Reduce interference and stay conservative | Yes |  |  | Document exact dBm after firmware phase.
RSSI Degradation Threshold | -78 dBm | Routing/failover | From project document; conservative quality threshold | Yes |  |  | Not hard LoRa failure threshold.
RSSI Critical Threshold | -95 dBm | Routing/failover | More realistic LoRa degradation marker | Yes |  |  | Tune after field tests.
Failover Delay | 10 seconds | Gateway logic | From project document | Yes |  |  | Trigger after stable failure condition.
Recovery Stable Time | 10 seconds | Gateway logic | Avoid flapping | Yes |  |  | Revert only after stable link.
Satellite Sim Latency | 500-700 ms | Pi tc/netem | Project target | Yes |  |  | Apply on gateway interface.
Max Hop Count | 3 | ESP32 mesh | Small six-node prototype | Yes |  |  | Increase only after testing.
ACK Retry Count | 3 | Messaging protocol | Reliability vs airtime balance | Yes |  |  | Tune after PDR tests.
Destination Not Local Rule | Route to next network via gateway | Gateway logic | User requirement | No |  |  | If destination unknown locally, forward to remote gateway.
Codex/GitHub Configuration Tracker
Item | Recommended Value | Actual Value | Where Set | Owner | Status | Evidence | Notes
GitHub Repository | pup-manet-emergency-messaging |  | GitHub | User | Not Started | Repo URL
Local Repo Path | MacBook Pro local project folder |  | Mac Finder/Terminal | User | Not Started | pwd output
Codex Local Tool | Installed on MacBook Pro M1 Max | Installed | Mac terminal | User | Available | codex --version output | User confirmed installed.
Codex Cloud/GitHub | Connect repo to Codex when ready |  | Codex settings | User | Not Started | Codex environment screenshot/link
AGENTS.md | Root-level project instructions file |  | Repo root | Codex/User | Not Started | Commit hash
Default Branch | main |  | GitHub | User | Not Started | GitHub screenshot
Workbook Location | docs/workbook/PUP_MANET_Implementation_Workbook.xlsx |  | GitHub repo | User | Not Started | Commit hash
Diagrams Location | docs/diagrams/ |  | GitHub repo | User | Not Started | Commit hash

## Packet Protocol
Proposed Packet Protocol
Packet Type | Required Fields | Purpose | ACK Required? | Stored? | Example | ESP32 Role | Gateway Role
HELLO | type,node_id,network_id,battery,rssi_last,snr_last,uptime | Neighbor discovery and health | No | Latest only | HELLO A1 NET_A batt=82 | Broadcast periodically | Update node table
MSG | type,msg_id,src,dst,network_id,payload,ttl,path,timestamp | User text message | Yes | Yes | A1 to B2: emergency text | Forward/receive/ACK | Route local or remote
ACK | type,msg_id,src,dst,status,path,timestamp | Confirm delivery or relay acceptance | No | Yes | ACK for MSG123 | Return to previous hop | Update delivery state
ROUTE_ADV | type,gateway_id,network_id,metric,hop_count | Gateway/route advertisement | No | Latest only | GWA advertises NET_A | Store route score | Advertise network reachability
NACK | type,msg_id,reason,last_hop | Signal failure | No | Yes | Destination unreachable | Try alternate route | Trigger gateway forwarding

## Routing & Failover
Routing & Failover Logic - Test-Aligned
Mode | Trigger | Primary Action | Fallback Action | Required Log Fields | Acceptance Criteria | Development Phase | Status
Baseline | Startup / stable links | 6 nodes discover neighbors and exchange LoRa messages | Keep simulated satellite inactive | startup_time, neighbor_count, pdr, rssi, snr | MANET forms ≤30 sec; PDR ≥95%; satellite inactive | ESP32 + RPi simulation | Pending
Degradation Detection | RSSI < -78 dBm for 10 sec or repeated ACK failure | Mark route degraded; record event | Prepare gateway failover route | rssi_min, snr, ack_fail_count, degrade_start, degrade_end | Degradation detected after 10 sec | ESP32 + RPi simulation | Pending
Failover Activation | Route unavailable or destination not found locally | Gateway forwards via WiFi-router simulated satellite | Use GSM only if explicitly selected/available | failover_start, failover_end, route_used, queue_depth | Failover trigger time = 10 sec | RPi gateway | Pending
Store & Forward | High latency or receiver unavailable | Queue messages and retry until ACK | Preserve FIFO order | message_id, retry_count, queue_time, ack_time | No message loss during recovery test | RPi gateway | Pending
Recovery | MANET route stable for 10 sec | Switch back to primary LoRa route | Deactivate simulated satellite path for normal traffic | recovery_start, recovery_end, route_before, route_after | Switchback ≤5 sec; no message loss | RPi gateway | Pending
Manual App Selection | User selects LoRa / WiFi / GSM | Use selected interface when available | Show unavailable warning if selected path fails | selected_network, actual_network, error | Manual mode must not break Auto mode tests | Android app | Pending

## Simulation Plan
Simulation-First Development Plan
Simulation Item | Description | Output File/Module | Inputs | Expected Output | Pass Criteria | Priority | Status | Notes
Node simulator | Emulates ESP32 node behavior: HELLO, MSG, ACK, retry, battery | sim_node.py | Node ID, network ID, links | Console/log packets | 6 nodes run simultaneously | High | Not Started
Gateway simulator | Emulates Pi gateway and inter-network routing | sim_gateway.py | GWA/GWB config | Routes unknown destinations to other network | A1 to B2 delivery works | High | Not Started
Network fault simulator | Drops packets, lowers RSSI, adds delay | sim_faults.py | Fault profile | Failover/recovery events | Failover at 10s | High | Not Started
Message store | SQLite or JSONL logs for messages and events | messages.db/logs | Packets/events | Traceable delivery status | No duplicate delivered messages | High | Not Started
Dashboard mock | Optional local web view for simulation | Flask app | Sim state | Node and route display | Usable before hardware | Medium | Not Started

## Android App Plan
Android Messaging App Plan - App-First Simulation Baseline
Step | Feature | Purpose | Minimum Requirement | Simulation Behavior | Real Hardware Later | Interface | Status | Validation | Notes
A1 | Project skeleton | Create Android app foundation | Kotlin app under android-chat-app; buildable project; README; task log | Runs empty/home screen | None yet | Android Studio / Gradle | Completed | Android Studio project builds and runs locally | Android Steps 001-012 completed and validated through emulator testing.
A2 | Chat screen | Show messaging workflow | Message list, compose field, send button | Messages appear locally with route and status | Later connect to gateway or ESP32 | UI | Completed | Chat UI operational with message cards and send workflow | Android Steps 001-012 completed and validated through emulator testing.
A3 | Manual network selection | User can choose route | AUTO, WIFI, GSM, LORA selector visible | Selected route applied to outgoing simulated message | Later map to real Android APIs/Bluetooth | UI state | Completed | AUTO / LoRa / WiFi / GSM route selection validated | Android Steps 001-012 completed and validated through emulator testing.
A4 | Auto mode logic | Prepare best-route selection | Mock availability and priority rules | If WiFi/GSM unavailable, route to LoRa | Later use real APIs/status | Local simulator | Completed | Adaptive routing and failover simulation working | Android Steps 001-012 completed and validated through emulator testing.
A5 | Message status model | Validation evidence | Queued, Sent, Delivered, Failed states | Simulated ACK/delivery confirmation | Later ACK from ESP32/gateway | Data model | Completed | Queued / Routing / Relaying / Delivered / Failed states working | Android Steps 001-012 completed and validated through emulator testing.
A6 | Bluetooth interface placeholder | Prepare phone-to-ESP32 pairing | Permission entries and service class/interface | Mock connected/disconnected paired node | Later implement BLE/SPP | Android Bluetooth API | Completed | Bluetooth placeholder pairing simulation operational | Android Steps 001-012 completed and validated through emulator testing.
A7 | GSM/WiFi placeholders | Prepare manual transport choices | Interface abstraction only | Mock available/unavailable status | Later Android SMS/network implementation if needed | Transport interface | Completed | Transport abstraction placeholders operational | Android Steps 001-012 completed and validated through emulator testing.
A8 | Return checkpoint | Resume hardware work | Document exact resume point in workbook | N/A | Return to ESP32 Step 003/004 | Workbook | Completed | Workbook and GitHub workflow synchronized | Android Steps 001-012 completed and validated through emulator testing.

## Test Campaign
Test Campaign - Pass/Fail Mapping to Updated Diagrams
Test | System Mode | Required Setup | Procedure Focus | Measured Parameters | Acceptance Criteria | Diagram Reference | Workbook Reference | Evidence to Capture | Status
Baseline Operation | Normal LoRa MANET | 6 ESP32 LoRa nodes, 2 gateways, satellite routers inactive | Auto-discovery and periodic text packets | RSSI, SNR, hop count, PDR, latency | PDR ≥95%; MANET forms ≤30 sec; satellite inactive | System Diagram + Data Flow steps 1-4 | Routing & Failover row Baseline | Startup logs, PDR report, screenshot | Pending
Network Degradation Detection | Degraded MANET | Same as baseline with distance/attenuation introduced | Lower RSSI until threshold condition | RSSI trend, detection time, route change | RSSI < -78 dBm for 10 sec must be detected | Control Logic block | Routing & Failover row Degradation Detection | RSSI log graph/table | Pending
Failover Activation | Failover via simulated satellite | MANET active, WiFi router-to-router link available | Route unavailable or destination not found locally | Trigger time, gateway status, queue depth | Failover trigger time = 10 sec | System Diagram failover path; Data Flow step 5 | Routing & Failover row Failover Activation | Gateway logs + message delivery proof | Pending
Sustained Emergency Operation | Emergency operation | Battery-powered nodes and gateways running | Run for 24 hours with controlled events | Uptime, battery, route stability, queue health | Uptime ≥80%; no crash/deadlock | System Diagram test-critical logic | Simulation Plan + Progress Tracker | 24-hour service logs | Pending
Recovery and Reversion | Recovery mode | Start in failover, then restore MANET link quality | Stable RSSI for 10 sec then switch back | Recovery time, packet loss, route before/after | Switchback ≤5 sec; no message loss | Data Flow recovery row | Routing & Failover row Recovery | Route-change logs + message ACKs | Pending

## Progress Tracker
Progress Log
Date | Step ID | What Was Done | Result | Evidence | Updated By | Next Step | Notes
2026-05-10 | 002/003 | ESP32 PlatformIO simulation compiled and uploaded; serial monitor confirmed messages are received/forwarded | Partially validated; parser fix still pending | Local PlatformIO build/upload log and serial monitor output | User + ChatGPT | Pivot to Android app skeleton | Resume ESP32 parser validation after Android baseline
2026-05-10 | D5/A1 | Workbook updated for Android-first Codex/GitHub workflow | Ready for Android app first task | Updated workbook | ChatGPT | Run Codex Android A1 prompt | Do not lose ESP32 return point
2026-05-11 14:01 | ANDROID-001-012 | Completed Android MANET simulation app baseline through Step 012 including routing, failover, queue engine, validation system, tabbed UI, logs, Bluetooth placeholder, and adaptive routing engine. | Validated on Android emulator and GitHub | 2026-05-11 | User + ChatGPT | Proceed to Android Step 013 real transport integration planning | Main branch now contains android-chat-app source code.
2026-05-11 14:01 | GITHUB-MERGE | Merged Android development branch into main repository branch | Successful merge | GitHub repository history | User | Continue Android enhancement | Kotlin now visible in GitHub language statistics.

## Issue Log
Issue / Troubleshooting Log
Issue ID | Date | Step ID | Problem | Error / Symptom | Root Cause | Fix Applied | Status | Notes

## Decision Log
Design Decision Log
Decision ID | Date | Decision | Reason | Alternatives Considered | Impact | Status | Notes
D1 | 2026-05-04 | Use simulation-first workflow | User has physical nodes but wants to start with simulation | Hardware-first development | Reduces debugging risk | Accepted
D2 | 2026-05-04 | Start with controlled reliable mesh instead of full AODV | AODV on LoRa ESP32 is complex and hard to debug initially | Full AODV immediately | Faster prototype; can evolve later | Recommended
D3 | 2026-05-04 | If destination is not local, route to next network via gateway | User requirement | Drop unknown destinations | Enables Network A to B messaging | Accepted
D4 | 2026-05-04 | Develop ESP32 code, then Raspberry Pi gateway, then Android app | User requested order | Android first | Ensures app integrates with stable backend | Accepted
D5 | 2026-05-10 | Pivot to build Android app before LoRa hardware | User requested Android app first and wants workbook to preserve exact return point | Continue ESP32 LoRa immediately | Android-first baseline added; ESP32 work paused at Step 003 parser validation | Accepted | Return to ESP32 Step 003/R1 after Android A1-A4 baseline
2026-05-05 | Development workflow | Use Codex Web + GitHub as primary and Codex CLI on Mac as secondary. VS Code optional only. | User confirmed Codex installed on MacBook Pro M1 Max and wants no VS Code dependency. | Accepted | Marvin/Project | Implementation workbook updated | Proceed to GitHub repo setup

## System Diagram
System Architecture Diagram - Test Procedure Aligned
Updated to prioritize DOCX test procedures: baseline MANET, RSSI degradation detection, failover activation, sustained operation, and recovery.

## Data Flow
Message / Data Flow Diagram - Test Procedure Aligned
Updated to prioritize DOCX test procedures: baseline MANET, RSSI degradation detection, failover activation, sustained operation, and recovery.

## Codex GitHub Workflow
Codex + GitHub Workflow — VS Code Optional
Stage | Tool | Where it runs | Purpose | Input required | Output expected | Who validates | Workbook update required | GitHub action | Pass condition | Notes
0. Baseline repo | GitHub + Codex Web | Browser | Create empty project repository and documentation baseline | Workbook, diagrams, DOCX test requirements | Repo with folders, README, AGENTS.md, docs | User + ChatGPT | Yes: Repo baseline complete | Initial commit | Repo opens and files are visible | No VS Code required
1. Codex instructions | Codex Web | Cloud | Create/verify AGENTS.md so Codex follows workbook and test procedures | Workbook step number and coding rules | AGENTS.md with project rules | User + ChatGPT | Yes: AGENTS.md approved | PR or direct commit | Codex follows scope and does not rewrite unrelated files | Every Codex task must cite workbook step
2. Local Codex CLI setup | Codex CLI | MacBook Pro M1 Max terminal | Allow local repo review and controlled edits without VS Code | GitHub repo cloned locally | Codex CLI can read project and propose edits | User | Yes: CLI setup evidence | Optional local branch commit | codex command runs in repo folder | Used for local checks/troubleshooting
3. ESP32 simulation | Codex Web or CLI | GitHub cloud/local Mac | Create PlatformIO project with simulation mode first | Step prompt + packet format | Compilable ESP32 code with simulated LoRa/messages | User + ChatGPT | Yes: build result and notes | PR | PlatformIO build passes | Hardware not required yet
4. ESP32 LoRa + Bluetooth | Codex Web or CLI | GitHub cloud/local Mac | Add SX1278 LoRa and Android Bluetooth bridge | Pin map, baud, Bluetooth pairing rules | Firmware supports phone-to-LoRa bridge | User hardware test | Yes: test evidence/screenshots | PR | Message sent from Android/serial reaches LoRa packet layer | Physical Bluetooth/LoRa tested by user
5. Raspberry Pi gateway simulation | Codex Web or CLI | Cloud/local Mac | Build Python gateway logic without hardware first | Packet protocol, failover rules | Gateway simulator, web dashboard/logs | User + ChatGPT | Yes: simulation test result | PR | Simulated 6-node traffic passes baseline/degradation/failover | Python tests can run in Codex
6. Raspberry Pi LoRa SPI | Codex Web or CLI | Repo + Raspberry Pi hardware | Add real SX1278 SPI support to gateway | Wiring/pin map | Gateway receives LoRa packets from nodes | User hardware test | Yes: hardware evidence | PR | Pi receives/sends LoRa packet reliably | Physical test cannot be completed by Codex alone
7. Router-to-router simulated satellite | Codex Web or CLI | Raspberry Pi + routers | Implement gateway-to-gateway WiFi path and latency simulation | Router IPs, network settings | Inter-gateway message forwarding | User hardware test | Yes: latency/log evidence | PR | Network A can route message to Network B | Use WiFi routers to simulate satellite path
8. Android app | Codex Web or CLI | GitHub cloud/local Mac | Create Android messaging app | UI requirements, network modes | Android Studio project | User + phone test | Yes: APK/build/test evidence | PR | App builds and can select Auto/WiFi/GSM/LoRa | Android Studio still used for build/run if needed
9. Integrated validation | Codex + User hardware | Physical setup | Run DOCX test campaign | 6 nodes, 2 gateways, 2 routers, phones | Completed test log and workbook evidence | User + ChatGPT | Yes: all test sheets updated | Final PR/Release tag | All acceptance criteria passed | Workbook is final continuation reference

## Codex Task Prompts
Codex Task Prompts — One Task Per Workbook Step
Task ID | Workbook Step | Use With | Prompt Title | Prompt | Expected Output | Allowed Files | Validation | Workbook Update
C0 | 0.1 | Codex Web | Create baseline repo | Create the repository structure for pup-manet-emergency-messaging. Add README.md, AGENTS.md, docs/workbook, docs/diagrams, docs/test-procedures, esp32-node-platformio, rpi-gateway, and android-chat-app folders. Do not implement application code yet. | Baseline repo structure | All top-level docs/folders | Repo opens and README explains workflow | Mark repo baseline complete
C1 | 1.1 | Codex Web | Write AGENTS.md | Create AGENTS.md for this project. Codex must follow the workbook step number, keep ESP32/RPi/Android separate, preserve test procedure alignment, avoid unrelated rewrites, and report validation commands/results. | AGENTS.md | AGENTS.md only unless README reference needed | AGENTS.md includes scope and validation rules | Mark Codex instruction baseline complete
C2 | 2.1 | Codex CLI | Inspect repo locally | Inspect this repository against AGENTS.md and the workbook. Do not modify files. Report missing folders, unclear setup, and recommended next task. | Review report only | No file changes | git status clean after task | Record local CLI inspection
C3 | 3.1 | Codex Web/CLI | ESP32 simulation project | Create the ESP32 PlatformIO project in esp32-node-platformio with simulation mode only. Implement message ID, source, destination, hop count, ACK/retry simulation, and serial logs. Do not add real LoRa hardware code yet. | Compilable PlatformIO project | esp32-node-platformio, README section | PlatformIO build passes | Record build output
C4 | 4.1 | Codex Web/CLI | ESP32 LoRa packet layer | Add SX1278 Ra-02 packet abstraction while preserving simulation mode. Use a hardware interface layer so simulation and physical LoRa can be selected by config. Include RSSI/SNR fields in received packet metadata. | LoRa abstraction + config | esp32-node-platformio | Build passes; simulation still works | Record build/test result
C5 | 4.2 | Codex Web/CLI | Bluetooth bridge | Add Bluetooth serial bridge for Android-to-ESP32 messaging. Preserve existing LoRa/simulation code. Include manual mode support placeholder: AUTO, LORA, WIFI, GSM. | Bluetooth bridge code | esp32-node-platformio | Build passes; serial/Bluetooth message parser test documented | Record Bluetooth test
C6 | 5.1 | Codex Web/CLI | RPi gateway simulator | Create rpi-gateway Python project with simulator for 6 MANET nodes, 2 gateways, and 2 WiFi-router satellite path. Implement routing, message buffer, ACK/retry, failover trigger after 10 seconds, and recovery after 10 seconds. | Python gateway simulator | rpi-gateway | Unit tests/simulation logs pass | Record simulation result
C7 | 8.1 | Codex Web/CLI | Android app skeleton | Create Android app skeleton for messaging. Include screens for chat, node pairing status, and network mode selection: AUTO, WIFI, GSM, LORA. Do not require real Bluetooth/GSM implementation in first task. | Android project skeleton | android-chat-app | Gradle build passes if environment configured | Record build result
ANDROID-FIRST CODEX TASKS
Task ID | Workbook Step | Use With | Prompt Title | Prompt | Expected Output | Allowed Files | Validation | Workbook Update
A1 | Android A1 | Codex Web/CLI | Android app skeleton | Create the Android app baseline first. Work only in android-chat-app and docs/codex-task-logs. Create a minimal buildable Android app in Kotlin. Include a simple home/chat screen placeholder, app name PUP MANET Messenger, README with build/open instructions, and docs/codex-task-logs/ANDROID_A1_APP_SKELETON.md. Do not implement real Bluetooth, GSM, WiFi, LoRa, or gateway logic yet. Do not modify esp32-node-platformio except if updating documentation references is absolutely necessary. | Buildable Android skeleton + README + task log | android-chat-app, docs/codex-task-logs | Gradle build if available; otherwise static project validation | Mark A1 complete after user build/screenshot
A2 | Android A2 | Codex Web/CLI | Chat UI simulation | Add local chat UI with message list, compose field, Send button, route badge, and mock sent/delivered state. Keep it simulation-only. | Chat UI | android-chat-app, docs/codex-task-logs | Screenshot or emulator/device run | Record evidence
A3 | Android A3 | Codex Web/CLI | Manual network selector | Add manual route selector: AUTO, WIFI, GSM, LORA. Selected mode must appear on outgoing messages. No real transport yet. | Network selector UI | android-chat-app, docs/codex-task-logs | Screenshot showing modes | Record evidence
A4 | Android A4 | Codex Web/CLI | Mock transport engine | Implement local mock transport engine for availability and fallback simulation. When WiFi/GSM unavailable, route message to LoRa in Auto mode. | Local simulation engine | android-chat-app, docs/codex-task-logs | Local simulation log or screenshot | Record evidence
R1 | Resume ESP32 | ChatGPT/User/Codex | Return to ESP32 work | After Android baseline, resume ESP32 Step 003 command parser validation and then Step 004 LoRa hardware layer. | Documented return | esp32-node-platformio | Serial monitor STATUS/NEIGHBORS/SEND works | Mark ESP32 resumed

## Repo Structure
Repository Structure — Codex/GitHub Source of Truth
Path | Purpose | Owned by | Generated/Edited by Codex | Hardware dependent | Build/Test command | Notes | Status | Last Updated
/README.md | Project overview and workflow | Project | Yes | No | N/A | Explains Codex-only workflow | Planned | 2026-05-05
/AGENTS.md | Codex operating rules | Project | Yes | No | N/A | Must be reviewed before coding | Planned | 2026-05-05
/docs/workbook/ | Workbook tracker | Project | User/ChatGPT | No | N/A | Updated after each completed step | Planned | 2026-05-05
/docs/diagrams/ | System and flow diagrams | Project | User/ChatGPT | No | N/A | Test-aligned diagrams | Planned | 2026-05-05
/docs/test-procedures/ | DOCX-derived validation references | Project | User/ChatGPT | No | N/A | Acceptance criteria live here | Planned | 2026-05-05
/esp32-node-platformio/ | ESP32 LoRa/Bluetooth node firmware | ESP32 | Yes | Yes | pio run | Simulation first, hardware later | Planned | 2026-05-05
/rpi-gateway/ | Raspberry Pi gateway service/dashboard | RPi | Yes | Partly | python -m pytest | Simulation first, SPI later | Planned | 2026-05-05
/android-chat-app/ | Android messaging app | Android | Yes | Partly | ./gradlew build | Manual Auto/WiFi/GSM/LoRa selection | Planned | 2026-05-05

## Codex CLI on Mac
Codex CLI on MacBook Pro M1 Max
Step | Command / Action | Purpose | Expected result | When to use | Workbook evidence | Risk / Warning | Status
1 | Create/clone GitHub repo locally | Prepare local project folder for Codex CLI | Repo folder exists on Mac | Before local Codex tasks | Screenshot or terminal output | Do not create duplicate unrelated folders | Planned
2 | cd pup-manet-emergency-messaging | Enter repo root before running Codex | Terminal path is repo root | Every CLI session | Terminal output | Running Codex outside repo may edit wrong folder | Planned
3 | codex | Start Codex CLI | Interactive Codex session opens | Local review/editing | Screenshot or note | Do not approve large rewrites without review | Planned
4 | Ask Codex to inspect only first | Prevent unnecessary rewrites | Codex reports findings before changing files | Before any coding task | Codex summary | Must keep changes scoped to workbook step | Planned
5 | Run local build/test commands | Verify code before commit/PR | Build/test output available | After Codex changes | Build log | Hardware tests still require actual devices | Planned
6 | git status / git diff | Review changed files | Only expected files changed | Before commit | Diff summary | Never commit secrets or local config | Planned
7 | Commit and push branch | Send work to GitHub | Branch visible in GitHub | After successful review | Commit hash | Use meaningful commit messages | Planned

## Android First Workflow
ANDROID-FIRST DEVELOPMENT PIVOT - RETURN POINT TRACKER
Item | Decision / Task | Reason | Allowed Scope | Blocked Scope | Owner | Codex/GitHub Action | Validation Evidence | Status | Return Point
D5 | Build Android app before LoRa hardware | User requested app-first development and wants workbook to preserve resume point | Android skeleton, UI, simulation mode, local message model, manual route selection | Do not depend on real ESP32 Bluetooth, real GSM, or real gateway yet | User + Codex | Create Android app project under android-chat-app | Gradle build, screenshots, task log | Accepted | After Android baseline, resume ESP32 Step 003 parser validation
A1 | Android project skeleton | Needed before UI and route selection | Kotlin Android app, minimal Gradle project, README, task log | No real Bluetooth/GSM/WiFi send yet | Codex | Branch android-step-a1-skeleton; PR; merge | Gradle build success or documented local environment limitation | Next | ESP32 paused at Step 003 command parser fix
A2 | Chat UI simulation | Demonstrate messaging concept before hardware | Chat screen, message list, compose box, send button, route badge | No internet/GSM/Bluetooth requirement | Codex | PR with UI components | Emulator or phone screenshot | Planned | Continue Android steps until app baseline ready
A3 | Network selector UI | Manual Auto/WiFi/GSM/LoRa choice per user requirement | Segmented control/dropdown; selected route shown on each sent message | No real transport implementation yet | Codex | PR with UI state model | Screenshot showing all modes | Planned | Return to ESP32 after A4 or A5
A4 | Local simulation engine | Allow app testing without hardware | Mock delivery states: queued, sent, delivered, failed; mock route status | No server/GSM/Bluetooth yet | Codex | PR with local simulator | Test log + screenshot | Planned | Resume hardware after app proves flow
A5 | Bluetooth design placeholder | Prepare for Android-to-ESP32 pairing later | Permission declarations, service interface, mock connected/disconnected status | No real pairing required in baseline | Codex | PR with interface only | Build success + README | Planned | Next real task: ESP32 Bluetooth bridge or LoRa layer
R1 | Resume ESP32 Step 003 | Preserve where we stopped | Retest STATUS, NEIGHBORS, SEND commands after pulling latest code | None | User + ChatGPT | Local PlatformIO test | Serial monitor output | Paused | This is the exact return point
R2 | Then LoRa hardware layer | Physical network step after Android baseline | SX1278 packet send/receive with same JSON payload | No Android dependency at first | Codex + User | New branch step-004-lora-layer | Two-node LoRa test log | Deferred | Use hardware details before coding

## ANDROID_PROGRESS_SUMMARY
Step | Status | Git Tag | Main Features | Validation
Android Step 009 | Completed | android-step-009 | Realistic MANET simulation and dynamic routing | Validated on emulator/device
Android Step 010 | Completed | android-step-010 | Tabbed UI and field usability improvements | Validated
Android Step 011 | Completed | android-step-011 | Message queue engine and lifecycle states | Validated
Android Step 012 | Completed | android-step-012 | Validation checklist framework | Validated
Android Step 013 | Completed | android-step-013 | ESP32 transport preparation | Validated
Android Step 014 | Completed | android-step-014 | Bluetooth architecture simulation layer | Validated
Android Step 015 | Completed | android-step-015 | Bluetooth packet protocol specification | Validated
Android Step 016 | Completed | android-step-016 | Bluetooth readiness and hardware test planning | Validated
NEXT RECOMMENDED STEPS
Step 017 - ESP32 firmware packet parser
Step 018 - ESP32 Bluetooth service
Step 019 - Android Bluetooth permissions
Step 020 - Android Bluetooth socket implementation
Step 021 - Android-to-ESP32 live packet testing
Step 022 - ESP32-to-ESP32 LoRa live testing
STEP 017 | Completed | step-017-esp32-packet-parser | ESP32 firmware packet parser and protocol validation | Git commit/tag validated

## NEXT_STEPS_ROADMAP
NEXT DEVELOPMENT ROADMAP |  | Workbook Updated | 2026-05-12 01:08:51
STEP 018 | ESP32 Bluetooth Service
STEP 019 | Android Bluetooth Permissions
STEP 020 | Android Bluetooth Socket Layer
STEP 021 | Android ↔ ESP32 Live Packet Testing
STEP 022 | ESP32 ↔ ESP32 LoRa Live Testing
STEP 023 | End-to-End Android ↔ LoRa ↔ Android Messaging
STEP 024 | Raspberry Pi Gateway Integration