## Dashboard
MANET Emergency Messaging Prototype - Dashboard
Total Steps | 31
Done | 0
In Progress | 1
Blocked | 0
Not Started | 29
Completion | 0%
Current Stage | 0 Baseline
Next Action | Review workbook sheets and confirm architecture
Recommended Current Architecture
Layer | Recommended Implementation | Reason | Status | Owner | Date | Evidence | Notes
User App | Android app later; web dashboard first | Avoids mobile complexity before backend and protocol are stable | Planned
Gateway | Raspberry Pi 3B + directly wired LoRa module | Matches user choice and enables local routing/failover logic | Planned
MANET Node | ESP32 + SX1278 Ra-02 433 MHz | Available hardware; good for prototype | Planned
Satellite Simulation | Two 2.4 GHz WiFi routers connected wirelessly; latency simulated on Pi | Practical simulation of LEO path without Starlink | Planned
Routing | Reliable controlled mesh now; AODV-like later | Lower risk and easier debugging | Planned
Current Design Update
Diagrams and workbook logic updated to prioritize the DOCX test campaign. Development should start with simulation, then ESP32 PlatformIO LoRa firmware, Raspberry Pi gateway services, and Android app.

## README
PUP MANET Implementation Workbook / Plan
Purpose | This workbook is the working implementation tracker for the low-cost emergency messaging MANET prototype. Update it after every completed step so a new chat can continue from the workbook.
Project Basis | MANET_UPdated.docx objectives: 6 MANET nodes total, ESP32 + SX1278 Ra-02 433 MHz, Raspberry Pi 3B gateway, WiFi router simulated LEO-satellite path, RSSI/SNR/hop/battery monitoring, reliable messaging, adaptive failover.
Implementation Order | 1) Simulation first. 2) ESP32 PlatformIO firmware. 3) Raspberry Pi gateway software. 4) Android messaging/chat app. 5) Full integrated testing.
Important Design Decision | Start with a controlled reliable LoRa mesh protocol instead of full AODV. Add AODV-like route discovery later after baseline messaging is stable.
Source References | Project document: MANET_UPdated.docx. Frequency reference: Meshtastic LoRa region table for PH_433/PH_868/PH_915. Regulatory caution: NTC SRD rules/non-interference basis.
How to Use | Complete one step at a time. Mark Status as Done only after validation passes. Fill Actual Result, Evidence, Date Completed, and Notes.

## Architecture
PUP MANET Test-Aligned Architecture Summary
Item | Updated Test-Aligned Decision | Reason / Acceptance Link | Status | Owner | Evidence | Date Completed | Notes
Primary validated path | Android App → Bluetooth → ESP32 LoRa Node → LoRa MANET → Raspberry Pi Gateway → WiFi-router simulated satellite → Remote Gateway → LoRa MANET → Bluetooth → Android App | Directly exercises baseline, failover, store-forward, recovery, and end-to-end delivery tests. | Approved for Phase 1
Node pairing | Each MANET node is paired to one Android phone over Bluetooth. | Ensures Android messaging app can still inject messages to LoRa when WiFi/GSM are unavailable. | Approved
Manual network selection | Android app shall support Auto, LoRa, WiFi, and GSM selection. | Extra feature allowed but must not interfere with DOCX validation path. | Approved
Auto mode behavior | Auto mode checks WiFi, GSM, and Bluetooth/LoRa availability, then selects best available route. | Allows failover decisions while preserving manual test control. | Approved
Failover trigger | RSSI below -78 dBm for 10 seconds OR route/ACK timeout triggers failover to simulated satellite path. | Matches network degradation and failover activation procedures. | Approved
Recovery trigger | Primary MANET route stable for 10 seconds triggers return to MANET; target switchback ≤5 seconds. | Matches recovery/reversion test procedure. | Approved
Message not found locally | If destination is not in current MANET network, gateway forwards message to next network through simulated satellite path. | Implements cross-network routing requirement. | Approved
Simulation first | All code shall include simulation mode before physical LoRa validation. | Allows controlled testing of RSSI/SNR/latency/failover without risking hardware delays. | Approved
Development Order | Simulation → ESP32 PlatformIO code → Raspberry Pi gateway code → Android chat app.

## Phase Plan
Staged Implementation Plan
Phase | Name | Goal | Primary Output | Entry Criteria | Exit Criteria | Main Tools | Status | Notes
0 | Project Baseline | Finalize architecture and workbook | Approved workbook and topology | User confirms direction | Workbook ready and first active step chosen | Excel/ChatGPT | In Progress | This file is the baseline plan.
1 | Simulation Core | Simulate 6 nodes and 2 gateways on Mac/Pi | Python simulator with routing/failover logs | Workbook approved | Message routing between Network A and B simulated | VS Code, Python | Not Started | No hardware needed yet.
2 | ESP32 LoRa Firmware | Build PlatformIO firmware for LoRa messaging | Firmware for node relay and serial debug | Simulation packet format frozen | Physical node-to-node message send/ACK works | VS Code, PlatformIO | Not Started | Start with 2 nodes, then 6.
3 | Raspberry Pi Gateway | Build gateway service and dashboard | Python service + Flask dashboard | ESP32 packet format stable | Gateway sends/receives LoRa and routes to WiFi path | Raspberry Pi 3B, Python | Not Started | Direct LoRa module on Pi.
4 | Router/Satellite Simulation | Connect two network gateways over WiFi routers | Inter-network messaging with artificial latency | Gateway API stable | Network A can deliver to Network B through WiFi path | Linux tc/netem, routers | Not Started | Use 500-700 ms delay.
5 | Android Chat App | Create Android messaging app | Android Studio project | Gateway REST/WebSocket API stable | Android app sends/receives via active transport | Android Studio Kotlin | Not Started | LoRa/WiFi/GSM transport awareness.
6 | Integrated Test Campaign | Validate acceptance criteria | Signed test results and logs | All components working | PDR, failover, recovery, uptime targets measured | Workbook + logs | Not Started | Use Test Campaign sheet.

## Detailed Steps
Detailed Step Tracker - Update After Every Completed Step
Step ID | Phase | Stage | Action / Procedure | Validation / Expected Result | Status | Owner | Date Started | Date Completed | Actual Result | Evidence / File / Screenshot | Notes
0.1 | 0 Baseline | Workbook | Review workbook sheets and confirm architecture | Architecture accepted or edits listed | In Progress
0.2 | 0 Baseline | Topology | Confirm 6-node topology: Network A has 3 nodes, Network B has 3 nodes, each with gateway and WiFi router | Topology confirmed | Not Started
0.3 | 0 Baseline | Frequency | Confirm prototype frequency and power setting for SX1278 Ra-02 433 MHz | Selected LoRa settings documented | Not Started
1.1 | 1 Simulation | Packet Model | Create JSON packet model for message, ACK, HELLO, route advert, gateway advert | Simulator accepts packet schema | Not Started
1.2 | 1 Simulation | Six Nodes | Simulate six nodes: A1-A3 and B1-B3 with two gateways GWA/GWB | All simulated nodes appear in log | Not Started
1.3 | 1 Simulation | Local Delivery | Send message from A1 to A2 and A3 through simulated local routing | Message delivered with ACK | Not Started
1.4 | 1 Simulation | Inter-network Delivery | When destination is not found locally, route message from Network A to Network B via gateway/WiFi path | A1 can send to B1/B2/B3 | Not Started
1.5 | 1 Simulation | Failover Logic | Simulate local link failure and activate WiFi-router path after 10 seconds | Failover logged and messages buffered/retried | Not Started
1.6 | 1 Simulation | Recovery Logic | Restore local path and revert after stable recovery time | Recovery logged with no duplicate delivery | Not Started
2.1 | 2 ESP32 | PlatformIO Project | Create ESP32 PlatformIO project with SX1278 library and node config | Project builds successfully | Not Started
2.2 | 2 ESP32 | LoRa Wiring Test | Wire one ESP32 to SX1278 and run send/receive test | Radio initializes and sends packets | Not Started
2.3 | 2 ESP32 | Two-node Test | Flash two ESP32 nodes and test text message + ACK | PDR >=95% at short range | Not Started
2.4 | 2 ESP32 | Six-node Test | Flash six nodes with IDs A1-A3/B1-B3 | All nodes send HELLO packets | Not Started
2.5 | 2 ESP32 | Battery Metric | Add battery percentage reading through voltage divider | Battery shown in HELLO packet | Not Started
3.1 | 3 Gateway | Pi LoRa Wiring | Connect SX1278 directly to Raspberry Pi 3B SPI | Pi can initialize radio | Not Started
3.2 | 3 Gateway | Python Gateway Service | Create Python service to receive/transmit LoRa packets | Gateway logs LoRa packets | Not Started
3.3 | 3 Gateway | Dashboard | Create Flask dashboard showing nodes, messages, routes, RSSI/SNR | Dashboard works on LAN | Not Started
3.4 | 3 Gateway | Message Database | Store messages, ACKs, route events, and errors in SQLite | Database persists after restart | Not Started
4.1 | 4 Router Simulation | Router Setup | Configure two WiFi routers for wireless connection/bridge simulation | Gateways can ping each other through routers | Not Started
4.2 | 4 Router Simulation | Latency Simulation | Apply 500-700 ms artificial delay using Linux tc/netem | Ping latency matches target | Not Started
4.3 | 4 Router Simulation | Cross-network Routing | Route messages from local gateway to remote gateway | A network can message B network | Not Started
5.1 | 5 Android | Requirements | Define Android screens, API endpoints, and transport states | App design approved | Not Started
5.2 | 5 Android | Android Project | Create Android Studio Kotlin project | App builds and runs on emulator/device | Not Started
5.3 | 5 Android | Gateway API Integration | Connect app to Pi gateway REST/WebSocket API | App sends and receives messages | Not Started
5.4 | 5 Android | Transport Status UI | Show LoRa/WiFi/GSM path status and message delivery state | User can see active route | Not Started
6.1 | 6 Testing | Baseline Test | Run baseline terrestrial LoRa messaging | PDR >=95%, MANET forms within 30s | Not Started
6.2 | 6 Testing | Degradation Test | Move nodes/attenuate signal and monitor RSSI/SNR | Degradation detected after threshold period | Not Started
6.3 | 6 Testing | Failover Test | Disable/degrade local path and trigger WiFi-router backhaul | Failover within configured delay | Not Started
6.4 | 6 Testing | Recovery Test | Restore local path and verify automatic reversion | Switch back within target; no message loss | Not Started
6.5 | 6 Testing | 24-hour Test | Run sustained emergency operation | Uptime >=80%, no unrecoverable crash | Not Started

## Hardware BOM
Hardware Bill of Materials and Notes
Item | Qty | Use | Recommended Spec | Already Available? | Priority | Risk | Validation Test | Status | Notes
ESP32 Dev Board | 6+ | MANET nodes | ESP32 WROOM-32 acceptable; ESP32-S3 optional | Yes/confirm | High | Pin/library differences | Blink + serial + LoRa init | Planned | Use same board type if possible.
SX1278 Ra-02 433 MHz | 8 | 6 nodes + 2 gateways | 433 MHz module with correct antenna | Yes/confirm | High | Regulatory/power limits; bad antenna | LoRa send/receive at short range | Planned | Use low power for prototype.
Raspberry Pi 3B | 2 | Gateways | Pi 3B with stable 5V supply | Confirm | High | SPI wiring, CPU limits | Python LoRa gateway receives packets | Planned | Use Lite OS if possible.
WiFi Router 2.4 GHz | 2 | Satellite simulation | Router that supports wireless bridge/repeater/client mode preferred | Yes | High | May not bridge wirelessly | Gateway ping test | Planned | If unsupported, use OpenWrt/travel router.
Android Phone | 1+ | Chat app testing | Android 8+ recommended | Confirm | Medium | Network permissions/background limits | Install APK, connect to gateway | Future | Start web dashboard first.
Li-ion Battery Pack | 6 | Portable nodes | 3.7V/5V boost or regulated 5V | Confirm | Medium | Voltage sag | Runtime and battery reading test | Future | Simulation first.

## Config Tracker
Configuration Tracker
Parameter | Default / Starting Value | Where Used | Reason | Can Change? | Updated Value | Date Updated | Notes
LoRa Frequency | 433 MHz / PH_433-compatible prototype setting | ESP32 + Pi LoRa | Available SX1278 Ra-02 hardware | Yes |  |  | Verify compliance for non-lab use.
LoRa TX Power | Start low; do not maximize during lab tests | ESP32 + Pi LoRa | Reduce interference and stay conservative | Yes |  |  | Document exact dBm after firmware phase.
RSSI Degradation Threshold | -78 dBm | Routing/failover | From project document; conservative quality threshold | Yes |  |  | Not hard LoRa failure threshold.
RSSI Critical Threshold | -95 dBm | Routing/failover | More realistic LoRa degradation marker | Yes |  |  | Tune after field tests.
Failover Delay | 10 seconds | Gateway logic | From project document | Yes |  |  | Trigger after stable failure condition.
Recovery Stable Time | 10 seconds | Gateway logic | Avoid flapping | Yes |  |  | Revert only after stable link.
Satellite Sim Latency | 500-700 ms | Pi tc/netem | Project target | Yes |  |  | Apply on gateway interface.
Max Hop Count | 3 | ESP32 mesh | Small six-node prototype | Yes |  |  | Increase only after testing.
ACK Retry Count | 3 | Messaging protocol | Reliability vs airtime balance | Yes |  |  | Tune after PDR tests.
Destination Not Local Rule | Route to next network via gateway | Gateway logic | User requirement | No |  |  | If destination unknown locally, forward to remote gateway.

## Packet Protocol
Proposed Packet Protocol
Packet Type | Required Fields | Purpose | ACK Required? | Stored? | Example | ESP32 Role | Gateway Role
HELLO | type,node_id,network_id,battery,rssi_last,snr_last,uptime | Neighbor discovery and health | No | Latest only | HELLO A1 NET_A batt=82 | Broadcast periodically | Update node table
MSG | type,msg_id,src,dst,network_id,payload,ttl,path,timestamp | User text message | Yes | Yes | A1 to B2: emergency text | Forward/receive/ACK | Route local or remote
ACK | type,msg_id,src,dst,status,path,timestamp | Confirm delivery or relay acceptance | No | Yes | ACK for MSG123 | Return to previous hop | Update delivery state
ROUTE_ADV | type,gateway_id,network_id,metric,hop_count | Gateway/route advertisement | No | Latest only | GWA advertises NET_A | Store route score | Advertise network reachability
NACK | type,msg_id,reason,last_hop | Signal failure | No | Yes | Destination unreachable | Try alternate route | Trigger gateway forwarding

## Routing & Failover
Routing & Failover Logic - Test-Aligned
Mode | Trigger | Primary Action | Fallback Action | Required Log Fields | Acceptance Criteria | Development Phase | Status
Baseline | Startup / stable links | 6 nodes discover neighbors and exchange LoRa messages | Keep simulated satellite inactive | startup_time, neighbor_count, pdr, rssi, snr | MANET forms ≤30 sec; PDR ≥95%; satellite inactive | ESP32 + RPi simulation | Pending
Degradation Detection | RSSI < -78 dBm for 10 sec or repeated ACK failure | Mark route degraded; record event | Prepare gateway failover route | rssi_min, snr, ack_fail_count, degrade_start, degrade_end | Degradation detected after 10 sec | ESP32 + RPi simulation | Pending
Failover Activation | Route unavailable or destination not found locally | Gateway forwards via WiFi-router simulated satellite | Use GSM only if explicitly selected/available | failover_start, failover_end, route_used, queue_depth | Failover trigger time = 10 sec | RPi gateway | Pending
Store & Forward | High latency or receiver unavailable | Queue messages and retry until ACK | Preserve FIFO order | message_id, retry_count, queue_time, ack_time | No message loss during recovery test | RPi gateway | Pending
Recovery | MANET route stable for 10 sec | Switch back to primary LoRa route | Deactivate simulated satellite path for normal traffic | recovery_start, recovery_end, route_before, route_after | Switchback ≤5 sec; no message loss | RPi gateway | Pending
Manual App Selection | User selects LoRa / WiFi / GSM | Use selected interface when available | Show unavailable warning if selected path fails | selected_network, actual_network, error | Manual mode must not break Auto mode tests | Android app | Pending

## Simulation Plan
Simulation-First Development Plan
Simulation Item | Description | Output File/Module | Inputs | Expected Output | Pass Criteria | Priority | Status | Notes
Node simulator | Emulates ESP32 node behavior: HELLO, MSG, ACK, retry, battery | sim_node.py | Node ID, network ID, links | Console/log packets | 6 nodes run simultaneously | High | Not Started
Gateway simulator | Emulates Pi gateway and inter-network routing | sim_gateway.py | GWA/GWB config | Routes unknown destinations to other network | A1 to B2 delivery works | High | Not Started
Network fault simulator | Drops packets, lowers RSSI, adds delay | sim_faults.py | Fault profile | Failover/recovery events | Failover at 10s | High | Not Started
Message store | SQLite or JSONL logs for messages and events | messages.db/logs | Packets/events | Traceable delivery status | No duplicate delivered messages | High | Not Started
Dashboard mock | Optional local web view for simulation | Flask app | Sim state | Node and route display | Usable before hardware | Medium | Not Started

## Android App Plan
Android Messaging App Plan - Bluetooth / WiFi / GSM / LoRa
Feature | Purpose | Minimum Requirement | Test Impact | Interface | Phase | Status | Notes
Bluetooth pairing to ESP32 node | Route messages to LoRa when WiFi/GSM are unavailable | Pair one phone to one MANET node; reconnect automatically | Required for end-to-end LoRa validation | Bluetooth Serial/BLE | Android Phase 1 | Pending | Start with classic Bluetooth SPP if ESP32 Android compatibility is acceptable; BLE if needed.
Auto network selection | Select best available route | Check WiFi, GSM, Bluetooth-LoRa status | Supports degraded/failover behavior | Android network APIs + BT status | Android Phase 2 | Pending | Auto should prefer local WiFi when valid, then GSM, then LoRa depending on policy; tests can force LoRa.
Manual route selection | User can choose LoRa, WiFi, or GSM | Dropdown or segmented control | Allows controlled test cases | UI setting | Android Phase 2 | Pending | Manual setting must show selected and actual route.
Message status | Show sent, queued, delivered, failed | Display ACK state and route used | Needed for validation evidence | Gateway/API + BT response | Android Phase 2 | Pending | Keep message IDs visible in debug mode.
Simulation mode | Test without real radios | Mock route status and message delivery | Used before hardware testing | Local mock service | Android Phase 0 | Pending | Important because development starts in simulation.

## Test Campaign
Test Campaign - Pass/Fail Mapping to Updated Diagrams
Test | System Mode | Required Setup | Procedure Focus | Measured Parameters | Acceptance Criteria | Diagram Reference | Workbook Reference | Evidence to Capture | Status
Baseline Operation | Normal LoRa MANET | 6 ESP32 LoRa nodes, 2 gateways, satellite routers inactive | Auto-discovery and periodic text packets | RSSI, SNR, hop count, PDR, latency | PDR ≥95%; MANET forms ≤30 sec; satellite inactive | System Diagram + Data Flow steps 1-4 | Routing & Failover row Baseline | Startup logs, PDR report, screenshot | Pending
Network Degradation Detection | Degraded MANET | Same as baseline with distance/attenuation introduced | Lower RSSI until threshold condition | RSSI trend, detection time, route change | RSSI < -78 dBm for 10 sec must be detected | Control Logic block | Routing & Failover row Degradation Detection | RSSI log graph/table | Pending
Failover Activation | Failover via simulated satellite | MANET active, WiFi router-to-router link available | Route unavailable or destination not found locally | Trigger time, gateway status, queue depth | Failover trigger time = 10 sec | System Diagram failover path; Data Flow step 5 | Routing & Failover row Failover Activation | Gateway logs + message delivery proof | Pending
Sustained Emergency Operation | Emergency operation | Battery-powered nodes and gateways running | Run for 24 hours with controlled events | Uptime, battery, route stability, queue health | Uptime ≥80%; no crash/deadlock | System Diagram test-critical logic | Simulation Plan + Progress Tracker | 24-hour service logs | Pending
Recovery and Reversion | Recovery mode | Start in failover, then restore MANET link quality | Stable RSSI for 10 sec then switch back | Recovery time, packet loss, route before/after | Switchback ≤5 sec; no message loss | Data Flow recovery row | Routing & Failover row Recovery | Route-change logs + message ACKs | Pending

## Progress Tracker
Progress Log
Date | Step ID | What Was Done | Result | Evidence | Updated By | Next Step | Notes

## Issue Log
Issue / Troubleshooting Log
Issue ID | Date | Step ID | Problem | Error / Symptom | Root Cause | Fix Applied | Status | Notes

## Decision Log
Design Decision Log
Decision ID | Date | Decision | Reason | Alternatives Considered | Impact | Status | Notes
D1 | 2026-05-04 | Use simulation-first workflow | User has physical nodes but wants to start with simulation | Hardware-first development | Reduces debugging risk | Accepted
D2 | 2026-05-04 | Start with controlled reliable mesh instead of full AODV | AODV on LoRa ESP32 is complex and hard to debug initially | Full AODV immediately | Faster prototype; can evolve later | Recommended
D3 | 2026-05-04 | If destination is not local, route to next network via gateway | User requirement | Drop unknown destinations | Enables Network A to B messaging | Accepted
D4 | 2026-05-04 | Develop ESP32 code, then Raspberry Pi gateway, then Android app | User requested order | Android first | Ensures app integrates with stable backend | Accepted

## System Diagram
System Architecture Diagram - Test Procedure Aligned
Updated to prioritize DOCX test procedures: baseline MANET, RSSI degradation detection, failover activation, sustained operation, and recovery.

## Data Flow
Message / Data Flow Diagram - Test Procedure Aligned
Updated to prioritize DOCX test procedures: baseline MANET, RSSI degradation detection, failover activation, sustained operation, and recovery.