## Dashboard
MANET Emergency Messaging Prototype - Dashboard
Total Steps | 31
Done | 0
In Progress | 1
Blocked | 0
Not Started | 29
Completion | 0%
Current Stage | 0 Baseline
Next Action | Review workbook sheets and confirm architecture
Recommended Current Architecture
Layer | Recommended Implementation | Reason | Status | Owner | Date | Evidence | Notes
User App | Android app later; web dashboard first | Avoids mobile complexity before backend and protocol are stable | Planned
Gateway | Raspberry Pi 3B + directly wired LoRa module | Matches user choice and enables local routing/failover logic | Planned
MANET Node | ESP32 + SX1278 Ra-02 433 MHz | Available hardware; good for prototype | Planned
Satellite Simulation | Two 2.4 GHz WiFi routers connected wirelessly; latency simulated on Pi | Practical simulation of LEO path without Starlink | Planned
Routing | Reliable controlled mesh now; AODV-like later | Lower risk and easier debugging | Planned

## README
PUP MANET Implementation Workbook / Plan
Purpose | This workbook is the working implementation tracker for the low-cost emergency messaging MANET prototype. Update it after every completed step so a new chat can continue from the workbook.
Project Basis | MANET_UPdated.docx objectives: 6 MANET nodes total, ESP32 + SX1278 Ra-02 433 MHz, Raspberry Pi 3B gateway, WiFi router simulated LEO-satellite path, RSSI/SNR/hop/battery monitoring, reliable messaging, adaptive failover.
Implementation Order | 1) Simulation first. 2) ESP32 PlatformIO firmware. 3) Raspberry Pi gateway software. 4) Android messaging/chat app. 5) Full integrated testing.
Important Design Decision | Start with a controlled reliable LoRa mesh protocol instead of full AODV. Add AODV-like route discovery later after baseline messaging is stable.
Source References | Project document: MANET_UPdated.docx. Frequency reference: Meshtastic LoRa region table for PH_433/PH_868/PH_915. Regulatory caution: NTC SRD rules/non-interference basis.
How to Use | Complete one step at a time. Mark Status as Done only after validation passes. Fill Actual Result, Evidence, Date Completed, and Notes.

## Architecture
System Architecture Recommendation
Component | Quantity | Role | Implementation Recommendation | Why | Risk | Mitigation | Status
ESP32 LoRa Node | 6 | MANET message endpoint/relay | Start in simulation mode, then deploy physical nodes | Keeps firmware simple and testable | LoRa routing bugs | Use message IDs, ACKs, retries, logs | Planned
Raspberry Pi 3B Gateway | 2 | Bridge between local LoRa network and WiFi router path | Direct SPI LoRa module to Pi; Python gateway service | Supports routing decisions and dashboard | SPI wiring/library issues | Test LoRa receive/send before routing | Planned
WiFi Router 2.4 GHz | 2 | Simulated satellite terminal/path | Wireless router-to-router link if supported; otherwise one router as AP and one as client/bridge | Matches available hardware | Consumer routers may not support wireless bridge | Use travel router/OpenWrt or cable fallback for lab only | Planned
Android App | 1 app | Messaging UI | Develop after gateway API is stable | Avoids premature app rewrite | API changes | Freeze REST/WebSocket API before Android phase | Planned
GSM Network | Optional later | Fallback path | Add after LoRa+WiFi failover works | SMS latency/cost/network dependency | Abstract transports behind common message API | Future
Added Diagram References
System Diagram | Editable system architecture diagram showing 2 networks, 6 MANET nodes, 2 gateways, 2 WiFi routers, Android users, and simulated satellite path.
Data Flow | Editable message/data flow diagram showing local delivery, next-network routing, failover, recovery, ACK/retry, and simulation mode.
Development Order | Simulation → ESP32 PlatformIO code → Raspberry Pi gateway code → Android chat app.

## Phase Plan
Staged Implementation Plan
Phase | Name | Goal | Primary Output | Entry Criteria | Exit Criteria | Main Tools | Status | Notes
0 | Project Baseline | Finalize architecture and workbook | Approved workbook and topology | User confirms direction | Workbook ready and first active step chosen | Excel/ChatGPT | In Progress | This file is the baseline plan.
1 | Simulation Core | Simulate 6 nodes and 2 gateways on Mac/Pi | Python simulator with routing/failover logs | Workbook approved | Message routing between Network A and B simulated | VS Code, Python | Not Started | No hardware needed yet.
2 | ESP32 LoRa Firmware | Build PlatformIO firmware for LoRa messaging | Firmware for node relay and serial debug | Simulation packet format frozen | Physical node-to-node message send/ACK works | VS Code, PlatformIO | Not Started | Start with 2 nodes, then 6.
3 | Raspberry Pi Gateway | Build gateway service and dashboard | Python service + Flask dashboard | ESP32 packet format stable | Gateway sends/receives LoRa and routes to WiFi path | Raspberry Pi 3B, Python | Not Started | Direct LoRa module on Pi.
4 | Router/Satellite Simulation | Connect two network gateways over WiFi routers | Inter-network messaging with artificial latency | Gateway API stable | Network A can deliver to Network B through WiFi path | Linux tc/netem, routers | Not Started | Use 500-700 ms delay.
5 | Android Chat App | Create Android messaging app | Android Studio project | Gateway REST/WebSocket API stable | Android app sends/receives via active transport | Android Studio Kotlin | Not Started | LoRa/WiFi/GSM transport awareness.
6 | Integrated Test Campaign | Validate acceptance criteria | Signed test results and logs | All components working | PDR, failover, recovery, uptime targets measured | Workbook + logs | Not Started | Use Test Campaign sheet.

## Detailed Steps
Detailed Step Tracker - Update After Every Completed Step
Step ID | Phase | Stage | Action / Procedure | Validation / Expected Result | Status | Owner | Date Started | Date Completed | Actual Result | Evidence / File / Screenshot | Notes
0.1 | 0 Baseline | Workbook | Review workbook sheets and confirm architecture | Architecture accepted or edits listed | In Progress
0.2 | 0 Baseline | Topology | Confirm 6-node topology: Network A has 3 nodes, Network B has 3 nodes, each with gateway and WiFi router | Topology confirmed | Not Started
0.3 | 0 Baseline | Frequency | Confirm prototype frequency and power setting for SX1278 Ra-02 433 MHz | Selected LoRa settings documented | Not Started
1.1 | 1 Simulation | Packet Model | Create JSON packet model for message, ACK, HELLO, route advert, gateway advert | Simulator accepts packet schema | Not Started
1.2 | 1 Simulation | Six Nodes | Simulate six nodes: A1-A3 and B1-B3 with two gateways GWA/GWB | All simulated nodes appear in log | Not Started
1.3 | 1 Simulation | Local Delivery | Send message from A1 to A2 and A3 through simulated local routing | Message delivered with ACK | Not Started
1.4 | 1 Simulation | Inter-network Delivery | When destination is not found locally, route message from Network A to Network B via gateway/WiFi path | A1 can send to B1/B2/B3 | Not Started
1.5 | 1 Simulation | Failover Logic | Simulate local link failure and activate WiFi-router path after 10 seconds | Failover logged and messages buffered/retried | Not Started
1.6 | 1 Simulation | Recovery Logic | Restore local path and revert after stable recovery time | Recovery logged with no duplicate delivery | Not Started
2.1 | 2 ESP32 | PlatformIO Project | Create ESP32 PlatformIO project with SX1278 library and node config | Project builds successfully | Not Started
2.2 | 2 ESP32 | LoRa Wiring Test | Wire one ESP32 to SX1278 and run send/receive test | Radio initializes and sends packets | Not Started
2.3 | 2 ESP32 | Two-node Test | Flash two ESP32 nodes and test text message + ACK | PDR >=95% at short range | Not Started
2.4 | 2 ESP32 | Six-node Test | Flash six nodes with IDs A1-A3/B1-B3 | All nodes send HELLO packets | Not Started
2.5 | 2 ESP32 | Battery Metric | Add battery percentage reading through voltage divider | Battery shown in HELLO packet | Not Started
3.1 | 3 Gateway | Pi LoRa Wiring | Connect SX1278 directly to Raspberry Pi 3B SPI | Pi can initialize radio | Not Started
3.2 | 3 Gateway | Python Gateway Service | Create Python service to receive/transmit LoRa packets | Gateway logs LoRa packets | Not Started
3.3 | 3 Gateway | Dashboard | Create Flask dashboard showing nodes, messages, routes, RSSI/SNR | Dashboard works on LAN | Not Started
3.4 | 3 Gateway | Message Database | Store messages, ACKs, route events, and errors in SQLite | Database persists after restart | Not Started
4.1 | 4 Router Simulation | Router Setup | Configure two WiFi routers for wireless connection/bridge simulation | Gateways can ping each other through routers | Not Started
4.2 | 4 Router Simulation | Latency Simulation | Apply 500-700 ms artificial delay using Linux tc/netem | Ping latency matches target | Not Started
4.3 | 4 Router Simulation | Cross-network Routing | Route messages from local gateway to remote gateway | A network can message B network | Not Started
5.1 | 5 Android | Requirements | Define Android screens, API endpoints, and transport states | App design approved | Not Started
5.2 | 5 Android | Android Project | Create Android Studio Kotlin project | App builds and runs on emulator/device | Not Started
5.3 | 5 Android | Gateway API Integration | Connect app to Pi gateway REST/WebSocket API | App sends and receives messages | Not Started
5.4 | 5 Android | Transport Status UI | Show LoRa/WiFi/GSM path status and message delivery state | User can see active route | Not Started
6.1 | 6 Testing | Baseline Test | Run baseline terrestrial LoRa messaging | PDR >=95%, MANET forms within 30s | Not Started
6.2 | 6 Testing | Degradation Test | Move nodes/attenuate signal and monitor RSSI/SNR | Degradation detected after threshold period | Not Started
6.3 | 6 Testing | Failover Test | Disable/degrade local path and trigger WiFi-router backhaul | Failover within configured delay | Not Started
6.4 | 6 Testing | Recovery Test | Restore local path and verify automatic reversion | Switch back within target; no message loss | Not Started
6.5 | 6 Testing | 24-hour Test | Run sustained emergency operation | Uptime >=80%, no unrecoverable crash | Not Started

## Hardware BOM
Hardware Bill of Materials and Notes
Item | Qty | Use | Recommended Spec | Already Available? | Priority | Risk | Validation Test | Status | Notes
ESP32 Dev Board | 6+ | MANET nodes | ESP32 WROOM-32 acceptable; ESP32-S3 optional | Yes/confirm | High | Pin/library differences | Blink + serial + LoRa init | Planned | Use same board type if possible.
SX1278 Ra-02 433 MHz | 8 | 6 nodes + 2 gateways | 433 MHz module with correct antenna | Yes/confirm | High | Regulatory/power limits; bad antenna | LoRa send/receive at short range | Planned | Use low power for prototype.
Raspberry Pi 3B | 2 | Gateways | Pi 3B with stable 5V supply | Confirm | High | SPI wiring, CPU limits | Python LoRa gateway receives packets | Planned | Use Lite OS if possible.
WiFi Router 2.4 GHz | 2 | Satellite simulation | Router that supports wireless bridge/repeater/client mode preferred | Yes | High | May not bridge wirelessly | Gateway ping test | Planned | If unsupported, use OpenWrt/travel router.
Android Phone | 1+ | Chat app testing | Android 8+ recommended | Confirm | Medium | Network permissions/background limits | Install APK, connect to gateway | Future | Start web dashboard first.
Li-ion Battery Pack | 6 | Portable nodes | 3.7V/5V boost or regulated 5V | Confirm | Medium | Voltage sag | Runtime and battery reading test | Future | Simulation first.

## Config Tracker
Configuration Tracker
Parameter | Default / Starting Value | Where Used | Reason | Can Change? | Updated Value | Date Updated | Notes
LoRa Frequency | 433 MHz / PH_433-compatible prototype setting | ESP32 + Pi LoRa | Available SX1278 Ra-02 hardware | Yes |  |  | Verify compliance for non-lab use.
LoRa TX Power | Start low; do not maximize during lab tests | ESP32 + Pi LoRa | Reduce interference and stay conservative | Yes |  |  | Document exact dBm after firmware phase.
RSSI Degradation Threshold | -78 dBm | Routing/failover | From project document; conservative quality threshold | Yes |  |  | Not hard LoRa failure threshold.
RSSI Critical Threshold | -95 dBm | Routing/failover | More realistic LoRa degradation marker | Yes |  |  | Tune after field tests.
Failover Delay | 10 seconds | Gateway logic | From project document | Yes |  |  | Trigger after stable failure condition.
Recovery Stable Time | 10 seconds | Gateway logic | Avoid flapping | Yes |  |  | Revert only after stable link.
Satellite Sim Latency | 500-700 ms | Pi tc/netem | Project target | Yes |  |  | Apply on gateway interface.
Max Hop Count | 3 | ESP32 mesh | Small six-node prototype | Yes |  |  | Increase only after testing.
ACK Retry Count | 3 | Messaging protocol | Reliability vs airtime balance | Yes |  |  | Tune after PDR tests.
Destination Not Local Rule | Route to next network via gateway | Gateway logic | User requirement | No |  |  | If destination unknown locally, forward to remote gateway.

## Packet Protocol
Proposed Packet Protocol
Packet Type | Required Fields | Purpose | ACK Required? | Stored? | Example | ESP32 Role | Gateway Role
HELLO | type,node_id,network_id,battery,rssi_last,snr_last,uptime | Neighbor discovery and health | No | Latest only | HELLO A1 NET_A batt=82 | Broadcast periodically | Update node table
MSG | type,msg_id,src,dst,network_id,payload,ttl,path,timestamp | User text message | Yes | Yes | A1 to B2: emergency text | Forward/receive/ACK | Route local or remote
ACK | type,msg_id,src,dst,status,path,timestamp | Confirm delivery or relay acceptance | No | Yes | ACK for MSG123 | Return to previous hop | Update delivery state
ROUTE_ADV | type,gateway_id,network_id,metric,hop_count | Gateway/route advertisement | No | Latest only | GWA advertises NET_A | Store route score | Advertise network reachability
NACK | type,msg_id,reason,last_hop | Signal failure | No | Yes | Destination unreachable | Try alternate route | Trigger gateway forwarding

## Routing & Failover
Routing and Failover Logic
Rule ID | Condition | Action | Reason | Where Implemented | Test Case | Status | Notes
R1 | Destination node is in local neighbor/route table | Send through best local LoRa route | Lowest latency and preserves local MANET behavior | ESP32 + Gateway | A1 to A2 | Planned
R2 | Destination not found in current network | Forward to local gateway, then to next network gateway over WiFi-router path | User requirement for inter-network delivery | Gateway | A1 to B2 | Planned
R3 | RSSI below threshold for configured duration or no heartbeat | Mark route degraded and try alternate path | Avoid unreliable link | ESP32 + Gateway | Degradation test | Planned
R4 | All local route attempts fail after retries | Buffer message and forward through gateway if available | Preserve message delivery | ESP32 + Gateway | Failover test | Planned
R5 | Remote gateway unavailable | Queue message and retry with exponential/backoff interval | Delay-tolerant operation | Gateway | Router down test | Planned
R6 | Recovered route stable for recovery time | Revert to preferred local route and stop using backhaul for local messages | Avoid flapping and unnecessary backhaul use | Gateway | Recovery test | Planned

## Simulation Plan
Simulation-First Development Plan
Simulation Item | Description | Output File/Module | Inputs | Expected Output | Pass Criteria | Priority | Status | Notes
Node simulator | Emulates ESP32 node behavior: HELLO, MSG, ACK, retry, battery | sim_node.py | Node ID, network ID, links | Console/log packets | 6 nodes run simultaneously | High | Not Started
Gateway simulator | Emulates Pi gateway and inter-network routing | sim_gateway.py | GWA/GWB config | Routes unknown destinations to other network | A1 to B2 delivery works | High | Not Started
Network fault simulator | Drops packets, lowers RSSI, adds delay | sim_faults.py | Fault profile | Failover/recovery events | Failover at 10s | High | Not Started
Message store | SQLite or JSONL logs for messages and events | messages.db/logs | Packets/events | Traceable delivery status | No duplicate delivered messages | High | Not Started
Dashboard mock | Optional local web view for simulation | Flask app | Sim state | Node and route display | Usable before hardware | Medium | Not Started

## Android App Plan
Android Messaging / Chat System Plan
Module | Function | Initial Recommendation | Depends On | Transport Awareness | Validation | Status | Notes
Login/Device Setup | Connect phone to selected gateway | Use local gateway IP entry first; QR/manual config later | Gateway API | Shows connected gateway/network | Can connect to Pi dashboard API | Future
Chat Screen | Send/receive text messages | Simple conversation list and message composer | Message API | Shows Pending/Sent/Delivered/Failed | A1 phone sends to B2 | Future
Transport Status | Display LoRa/WiFi/GSM path used | Read route status from gateway, not phone decision first | Gateway routing logic | LoRa/WiFi/GSM labels | Correct route appears per message | Future
Offline Queue | Store messages until route available | Local Room database later | Stable API | Pending queue state | No lost unsent message | Future
GSM Option | SMS fallback | Add after LoRa+WiFi works | SIM/GSM design | GSM shown as fallback | SMS send/receive tested | Future | May require phone SMS permissions or separate GSM modem.

## Test Campaign
Validation Test Campaign
Test ID | Test Name | Setup | Procedure | Measured Parameters | Acceptance Criteria | Actual Result | Status | Evidence | Notes
T1 | Baseline Operation | 6 nodes, 2 gateways, stable LoRa links | Power on, auto-discover, send periodic messages | RSSI,SNR,hop,PDR,latency | PDR >=95%; MANET forms within 30s | Pending | Not Started
T2 | Network Degradation | Increase distance or simulate RSSI drop | Degrade until threshold duration reached | RSSI trend,detection time,route changes | Degradation detected after 10s | Pending | Not Started
T3 | Failover Activation | MANET active, router path ready | Disable/degrade local route | Trigger time, gateway status, delivery state | Failover activates and messages continue | Pending | Not Started
T4 | Sustained Emergency Operation | Battery nodes + gateways | Run 24 hours with fault events | Uptime,battery,routing stability | Uptime >=80%; no unrecoverable crash | Pending | Not Started
T5 | Recovery/Reversion | Start in backhaul mode | Restore local route above threshold | Recovery time, packet loss | Revert within target and no message loss | Pending | Not Started
T6 | Inter-network Delivery | Network A and B active | Send A1 to B2 when B2 not local | Route path, ACK, latency | Message forwarded to next network | Pending | Not Started

## Progress Tracker
Progress Log
Date | Step ID | What Was Done | Result | Evidence | Updated By | Next Step | Notes

## Issue Log
Issue / Troubleshooting Log
Issue ID | Date | Step ID | Problem | Error / Symptom | Root Cause | Fix Applied | Status | Notes

## Decision Log
Design Decision Log
Decision ID | Date | Decision | Reason | Alternatives Considered | Impact | Status | Notes
D1 | 2026-05-04 | Use simulation-first workflow | User has physical nodes but wants to start with simulation | Hardware-first development | Reduces debugging risk | Accepted
D2 | 2026-05-04 | Start with controlled reliable mesh instead of full AODV | AODV on LoRa ESP32 is complex and hard to debug initially | Full AODV immediately | Faster prototype; can evolve later | Recommended
D3 | 2026-05-04 | If destination is not local, route to next network via gateway | User requirement | Drop unknown destinations | Enables Network A to B messaging | Accepted
D4 | 2026-05-04 | Develop ESP32 code, then Raspberry Pi gateway, then Android app | User requested order | Android first | Ensures app integrates with stable backend | Accepted

## System Diagram
PUP MANET System Architecture Diagram
NETWORK A / LOCAL MANET CELL A | [5 empty] | NETWORK B / LOCAL MANET CELL B
| Android Phone A1 Chat User / UI |  | Android Phone A2 Chat User / UI |  |  |  | Android Phone B1 Chat User / UI |  | Android Phone B2 Chat User / UI
|  | ↓ WiFi / App API | ↓ WiFi / App API |  |  |  |  | ↓ WiFi / App API | ↓ WiFi / App API
|  | Android Phone A3 Chat User / UI | [5 empty] | Android Phone B3 Chat User / UI
|  | ↓ Message Inject | [5 empty] | ↓ Message Inject
| ESP32 LoRa Node A1 SX1278 Ra-02 |  | ESP32 LoRa Node A2 SX1278 Ra-02 |  |  |  | ESP32 LoRa Node B1 SX1278 Ra-02 |  | ESP32 LoRa Node B2 SX1278 Ra-02
|  | ↘ LoRa mesh ↙ | ↙ LoRa mesh ↘ |  |  |  |  | ↘ LoRa mesh ↙ | ↙ LoRa mesh ↘
|  | ESP32 LoRa Node A3 SX1278 Ra-02 | [5 empty] | ESP32 LoRa Node B3 SX1278 Ra-02
|  | ↓ Gateway uplink | [5 empty] | ↓ Gateway uplink
| Raspberry Pi 3B Gateway A LoRa SPI + WiFi Router Link Routing / Queue / Logs / API | [5 empty] | Raspberry Pi 3B Gateway B LoRa SPI + WiFi Router Link Routing / Queue / Logs / API
|  | ↓ WiFi route | [5 empty] | ↓ WiFi route
| 2.4 GHz WiFi Router A Satellite Path Simulator | [5 empty] | 2.4 GHz WiFi Router B Satellite Path Simulator
|  |  | ↘ |  |  |  | ↙
Simulated Satellite / Backhaul Link Router A ↔ Router B via WiFi Optional latency injection on Pi
|  |  |  | ──────────────▶ |  | ◀──────────────
Implementation Notes
1 | Simulation-first approach: Android app and gateways can use simulated nodes/messages before physical LoRa firmware is activated.
2 | Each network has 3 MANET nodes. If the destination user is not found in the current network, the gateway routes the message to the next network through the simulated satellite/WiFi router path.
3 | Raspberry Pi gateways are the decision points: they manage LoRa packets, message queues, routing tables, failover status, and app-facing APIs.

## Data Flow
PUP MANET Message and Data Flow Diagram
Flow Layer | Step 1 | Step 2 | Step 3 | Decision | Step 4A | Step 4B | Step 5 | Step 6 | Ack/Retry | Storage | Monitoring | Output | Status
User Message Creation | Android user types message | App checks local gateway connection | Message sent to Gateway API | Destination in same network? | Yes: send to local LoRa route | No: prepare inter-network route | Gateway queues message | Assign message_id + TTL | Retry until ACK or timeout | SQLite message log | RSSI/SNR/hop/battery status | Recipient receives message | Normal
Local LoRa Delivery | Gateway selects best local node | LoRa packet sent to relay/node | Node forwards if not recipient | ACK received? | Yes: mark delivered | No: retry or re-route | Duplicate filter checks message_id | Hop count increments | Max retries applied | Delivery record saved | Route quality updated | Delivery confirmation shown | Normal/Degraded
Inter-Network Routing | Gateway A checks user registry | Destination not local | Forward to WiFi Router A | Backhaul available? | Yes: route to Gateway B | No: buffer message | Router A ↔ Router B WiFi path | Gateway B receives message | ACK back to Gateway A | Queue retained until final ACK | Backhaul latency monitored | Message appears in Network B | Failover
Failover Trigger | Gateway monitors LoRa links | RSSI/SNR/heartbeat checked | Poor link lasts threshold time | Route degraded? | Yes: activate backhaul route | No: stay local MANET | Messages buffered during switch | Order preserved by timestamp/id | Failed packets retransmitted | Failover event logged | Dashboard status updates | User sees delayed/sent status | Emergency
Recovery/Reversion | Gateway detects stable local route | RSSI above threshold for stable period | Test packet confirms route | Return safe? | Yes: revert to preferred route | No: keep backhaul active | Flush queued messages | Final ACK validation | Retry missing messages | Logs retained | Dashboard shows recovered | App status returns normal | Recovered
Simulation Mode | Virtual nodes generated | Virtual RSSI/SNR/battery values | Virtual destination registry | Test scenario selected | Simulate normal/degraded/failover | No hardware required | Validate routing logic | Validate Android UI later | Validate ACK/retry logic | Simulated logs saved | Metrics plotted in dashboard | Ready for physical testing | Simulation
Simplified End-to-End Message Flow
Android Chat App Sender |  |  | Gateway A API + Queue |  |  | LoRa MANET A 3 Nodes |  |  | Gateway B API + Queue |  |  | Android Chat App Receiver
|  | ▶ |  |  | ▶ |  |  | ▶ |  |  | ▶
|  |  |  | ▼ |  |  |  |  | ▲
|  |  | If local route fails: Gateway A buffers + reroutes |  |  | WiFi Router A ↔ Router B Simulated Satellite Path |  |  | Gateway B injects message into Network B
[5 empty] | ▶ |  |  | ▶
Control / Monitoring Data Used for Routing Decisions
Metric | Source | Used By | Purpose | Initial Threshold / Rule | Workbook Tracker
RSSI | LoRa packet metadata | ESP32 nodes + Pi gateway | Detect link quality and choose route | Warning: -78 dBm; critical: tune during test | Config Tracker / Routing & Failover
SNR | LoRa packet metadata | Pi gateway routing service | Prefer cleaner LoRa route | Higher SNR preferred | Routing & Failover
Hop Count | Packet header | Nodes + gateway | Avoid long routes and loops | Max hop count: 3 initial | Packet Protocol
Message ACK | Recipient/gateway | Sender/gateway queue | Confirm delivery and trigger retry | Retry 3 times initial | Packet Protocol
Destination Registry | Gateway database | Gateway routing service | Determine local vs next-network routing | If not local, route to other network | Config Tracker
Backhaul Status | WiFi router ping/API | Pi gateway failover service | Activate inter-network path | 10 sec failure confirmation | Routing & Failover