## Dashboard
MANET Emergency Messaging Prototype - Dashboard
Total Steps
Done
In Progress
Blocked
Not Started
Completion
Current Stage
Next Action
Recommended Current Architecture
Layer | Recommended Implementation | Reason | Status | Owner | Date | Evidence | Notes
User App | Android app demo APK with Bluetooth-to-ESP32 typed-message flow | Supports current client demo without adding future GSM/broadcast scope | Demo APK Ready | Codex/User | 2026-05-13 | PUP-MANET-Messenger-Step023-Demo-debug.apk; physical phone-to-phone demo screenshots; commit 03d4cb0 | Demo validated addressed messaging over Bluetooth + ESP32 + LoRa. GSM and broadcast remain future workbook steps.
Gateway | Raspberry Pi 3B + directly wired LoRa module | Matches user choice and enables local routing/failover logic | SPI HAL Ready | Codex/User | 2026-05-13 | LoRa SPI heartbeat demo received A1/A2 heartbeats; 8 gateway tests passed. | Gateway simulation plus LoRa SPI HAL baseline ready. Physical Raspberry Pi/SX1278 driver bring-up remains future work.
MANET Node | ESP32 + SX1278 Ra-02 433 MHz | Available hardware; good for prototype | Planned
Satellite Simulation | Two 2.4 GHz WiFi routers connected wirelessly; latency simulated on Pi | Practical simulation of LEO path without Starlink | Planned
CURRENT DEVELOPMENT WORKFLOW UPDATE
Workflow | Codex + GitHub + Workbook tracking |  |  | Active Constraint | One workbook step per Codex task
Local Tool
Next Step
Workbook Rule | Update this workbook and commit it after every completed step |  |  | Status | Not Started
Workflow Update | Primary Tool | Secondary Tool | Code Source | Tracker | VS Code Role | Next Step | Status
2026-05-05 | Codex Web | Codex CLI on Mac | GitHub | Workbook | Optional only | Create GitHub repo baseline | Ready

## README
PUP MANET Emergency Messaging Workbook
Primary development workflow | Codex Web + GitHub pull requests. VS Code is optional and no longer required for the main workflow.
Local development workflow | Codex CLI on MacBook Pro M1 Max for local review, repo edits, build checks, and troubleshooting.
Repository source of truth | GitHub repository: pup-manet-emergency-messaging
Workbook source of truth | This workbook remains the project tracker. It must be updated after each completed Codex task and hardware validation step.
Development order | ESP32 PlatformIO simulation -> ESP32 LoRa/Bluetooth -> Raspberry Pi gateway simulation -> Raspberry Pi LoRa/WiFi router link -> Android messaging app -> integrated testing.
Test priority | All implementation must satisfy DOCX test procedures first: baseline, degradation detection, failover, sustained operation, and recovery.
Hardware testing note | Codex can create and test code logic, but physical LoRa, Bluetooth, WiFi router, and GSM validation must be performed by the user and recorded in this workbook.
Update date | 2026-05-05
Current workflow decision | Proceed with Codex-only workflow: Codex Web as primary, Codex CLI as secondary/local, GitHub as code storage, workbook as status control.

## Architecture
PUP MANET Test-Aligned Architecture Summary
Item | Updated Test-Aligned Decision | Reason / Acceptance Link | Status | Owner | Evidence | Date Completed | Notes
Primary validated path | Android App → Bluetooth → ESP32 LoRa Node → LoRa MANET → Raspberry Pi Gateway → WiFi-router simulated satellite → Remote Gateway → LoRa MANET → Bluetooth → Android App | Directly exercises baseline, failover, store-forward, recovery, and end-to-end delivery tests. | Approved for Phase 1
Node pairing | Each MANET node is paired to one Android phone over Bluetooth. | Ensures Android messaging app can still inject messages to LoRa when WiFi/GSM are unavailable. | Approved
Manual network selection | Android app shall support Auto, LoRa, WiFi, and GSM selection. | Extra feature allowed but must not interfere with DOCX validation path. | Approved
Auto mode behavior | Auto mode checks WiFi, GSM, and Bluetooth/LoRa availability, then selects best available route. | Allows failover decisions while preserving manual test control. | Approved
Failover trigger | RSSI below -78 dBm for 10 seconds OR route/ACK timeout triggers failover to simulated satellite path. | Matches network degradation and failover activation procedures. | Approved
Recovery trigger | Primary MANET route stable for 10 seconds triggers return to MANET; target switchback ≤5 seconds. | Matches recovery/reversion test procedure. | Approved
Message not found locally
Simulation first | All code shall include simulation mode before physical LoRa validation.
Development Order | Simulation → ESP32 PlatformIO code → Raspberry Pi gateway code → Android chat app.

## Phase Plan
STAGED IMPLEMENTATION PLAN — CODEX + GITHUB WORKFLOW
Phase | Name | Goal | Primary Output | Entry Criteria | Exit Criteria | Main Tools | Status | Notes
0 | Project Baseline | Finalize architecture and workbook | Approved workbook and topology | User confirms direction | Workbook ready and first active step chosen | Excel/ChatGPT | In Progress | This workbook is the continuity reference.
0.5 | GitHub + Codex Setup | Move development workflow into GitHub with Codex task control | Repository, AGENTS.md, README, workbook in docs/ | Workbook baseline available | Repo can be opened by VS Code/Codex and pushed to GitHub | GitHub, VS Code, Codex CLI/Cloud | Not Started | Added because user will develop using Codex on MacBook Pro M1 Max.
1 | Simulation Core | Simulate 6 nodes and 2 gateways before hardware | Python simulator with routing/failover logs | GitHub/Codex setup done | Message routing between Network A and B simulated | VS Code, Codex, Python | Not Started | No hardware needed yet.
2 | ESP32 Simulation Firmware | Start PlatformIO ESP32 code in simulation mode | Buildable PlatformIO project | Repo ready and packet format draft ready | Node simulation builds and logs message state | VS Code, PlatformIO, Codex | Not Started | Codex task C1.
3 | ESP32 LoRa Firmware | Add SX1278 Ra-02 LoRa messaging | Firmware for LoRa send/receive and ACK | ESP32 simulation stable | Physical node-to-node message send/ACK works | ESP32, PlatformIO, Codex | Not Started | Start with 2 nodes, then 6.
4 | Raspberry Pi Gateway | Build gateway service and dashboard | Python service + Flask dashboard | Protocol stable | Gateway sends/receives LoRa and routes to WiFi path | Raspberry Pi 3B, Python, Codex | Not Started | Direct LoRa module on Pi.
5 | Router/Satellite Simulation | Connect gateways over WiFi routers | Inter-network messaging with latency simulation | Gateway API stable | Network A can deliver to Network B through WiFi path | Routers, Linux tc/netem | Not Started | Use 500-700 ms delay.
6 | Failover/Recovery Test Logic | Implement and validate DOCX acceptance logic | State machine and test reports | Simulation and gateway stable | Pass baseline, degradation, failover, recovery tests | Codex, Python, PlatformIO | Not Started | RSSI < -78 dBm for 10s and stable 10s recovery.
7 | Android Chat App | Create Android messaging app | Android Studio project | Gateway/ESP32 protocol stable | App sends/receives via selected transport | Android Studio, Kotlin, Codex | Not Started | Manual Auto/LoRa/WiFi/GSM mode selection.
8 | Integrated Test Campaign | Validate acceptance criteria | Signed test results and logs | All components working | PDR, failover, recovery, uptime targets measured | Workbook + logs | Not Started | Update workbook after every passed step.
Codex-Only Development Overlay
Order | Phase | Primary tool | Secondary tool | Requires hardware | Repo area | Completion evidence | Workbook sheet to update | Status
1 | GitHub baseline | Codex Web | Codex CLI | FALSE | repo root + docs | Repo created and initial commit pushed | Codex GitHub Workflow / Repo Structure | Next
2 | ESP32 simulation | Codex Web | Codex CLI | FALSE | esp32-node-platformio | PlatformIO build log | Detailed Steps / Progress Tracker | Planned
3 | RPi gateway simulation | Codex Web | Codex CLI | FALSE | rpi-gateway | pytest/simulation log | Simulation Plan / Progress Tracker | Planned
4 | ESP32 LoRa + Bluetooth | Codex Web | Codex CLI | TRUE | esp32-node-platformio | Hardware test screenshots/logs | Config Tracker / Issue Log | Planned
5 | Gateway LoRa + WiFi routers | Codex Web | Codex CLI | TRUE | rpi-gateway | Inter-gateway routing test | Test Campaign / Progress Tracker | Planned
6 | Android app | Codex Web | Codex CLI + Android Studio | TRUE | android-chat-app | Build/app screenshots | Android App Plan / Progress Tracker | Planned

## Detailed Steps
DETAILED STEP TRACKER - UPDATE AFTER EVERY COMPLETED STEP
Step ID | Phase | Stage | Action / Procedure | Validation / Expected Result | Status | Owner | Date Started | Date Completed | Actual Result | Evidence / File / Screenshot | Notes
0.1 | 0 Baseline | Workbook | Review workbook sheets and confirm architecture | Architecture accepted or edits listed | In Progress | User + ChatGPT
0.2 | 0 Baseline | Topology | Confirm 6-node topology: Network A has 3 nodes, Network B has 3 nodes, each paired by Bluetooth to Android phone, with one gateway and one WiFi router per network | Topology confirmed | Not Started | User + ChatGPT
0.3 | 0 Baseline | Frequency | Confirm prototype frequency and power setting for SX1278 Ra-02 433 MHz | Selected LoRa settings documented | Not Started | User
0.4 | 0.5 GitHub/Codex | Repository | Create GitHub repository pup-manet-emergency-messaging | Repo exists and is accessible | Not Started | User |  |  |  | Repo URL
0.5 | 0.5 GitHub/Codex | Local Clone | Clone repo on MacBook Pro M1 Max and open in VS Code | Repo opens locally; git status clean | Not Started | User |  |  |  | Terminal output
0.6 | 0.5 GitHub/Codex | Repo Structure | Create required folders: esp32-node-platformio, rpi-gateway, android-chat-app, docs/workbook, docs/diagrams, docs/test-procedures, docs/codex-prompts | Folders exist | Not Started | User + Codex |  |  |  | tree output | Use Codex task C0 or manual setup.
0.7 | 0.5 GitHub/Codex | AGENTS.md | Add repository AGENTS.md with project rules for Codex | Codex instructions file exists | Not Started | Codex/User |  |  |  | File path + commit hash | Must require workbook step reference for all tasks.
0.8 | 0.5 GitHub/Codex | Workbook Commit | Copy latest workbook and diagrams into docs folder and commit to GitHub | Workbook and diagrams are versioned | Not Started | User |  |  |  | Commit hash | This workbook must be updated after every completed step.
0.9 | 0.5 GitHub/Codex | Codex Test Task | Run small Codex task to update README only | Codex completes task without touching unrelated files | Not Started | User + Codex |  |  |  | Codex task link or terminal output | Confirms Codex workflow before code development.
1.1 | 1 Simulation | Packet Model | Create JSON packet model for message, ACK, HELLO, route advert, gateway advert | Simulator accepts packet schema | Not Started | Codex |  |  |  | PR/commit + test log
1.2 | 1 Simulation | Six Nodes | Simulate six nodes: A1-A3 and B1-B3 with two gateways GWA/GWB | All simulated nodes appear in log | Not Started | Codex |  |  |  | Test log
1.3 | 1 Simulation | Local Delivery | Send message from A1 to A2 and A3 through simulated local routing | Message delivered with ACK | Not Started | Codex/User |  |  |  | Simulation log
1.4 | 1 Simulation | Cross Network Delivery | Send message from A1 to B1 via Gateway A -> WiFi router link -> Gateway B | Message reaches remote network with ordered delivery | Not Started | Codex/User |  |  |  | Simulation log
1.5 | 1 Simulation | Degradation Detection | Simulate RSSI below -78 dBm for 10 seconds | System changes to degraded/failover state | Not Started | Codex/User |  |  |  | Timestamped logs | DOCX test alignment.
1.6 | 1 Simulation | Recovery Detection | Simulate stable MANET link for 10 seconds and return to MANET within 5 seconds | Recovery succeeds with no message loss | Not Started | Codex/User |  |  |  | Timestamped logs | DOCX test alignment.
2.1 | 2 ESP32 Sim | PlatformIO Project | Create ESP32 PlatformIO project in simulation mode | pio run succeeds | Not Started | Codex |  |  |  | Build log | Use Codex task C1.
2.2 | 2 ESP32 Sim | Serial Debug | Print node ID, mode, queue status, and simulated link state to Serial Monitor | Readable serial output | Not Started | Codex/User |  |  |  | Serial screenshot
3.1 | 3 ESP32 LoRa | LoRa Wiring Doc | Document ESP32-to-SX1278 Ra-02 wiring and pin configuration | Wiring sheet/config updated | Not Started | Codex/User |  |  |  | Wiring doc
3.2 | 3 ESP32 LoRa | LoRa Send/Receive | Implement LoRa packet send/receive | Two nodes exchange packets | Not Started | Codex/User |  |  |  | Serial logs
3.3 | 3 ESP32 LoRa | ACK/Retry | Implement ACK, retry, duplicate filter | Message delivery improves under packet loss | Not Started | Codex/User |  |  |  | Serial logs
4.1 | 4 Gateway | Gateway Simulation | Create Python/Flask gateway simulation service | Runs on Mac/RPi in simulation mode | Completed | Codex |  | 2026-05-12 | Gateway simulator created under rpi-gateway; six-node/two-gateway simulation, gateway forwarding, buffering, ACK, 10-second failover, and 10-second recovery validated. | rpi-gateway tests passed; docs/codex-task-logs/STEP_024_RASPBERRY_PI_GATEWAY_INTEGRATION.md; commit 6bea5a5 | Simulation baseline only. Raspberry Pi SPI/SX1278 hardware integration remains later step.
4.2 | 4 Gateway | LoRa SPI Integration | Connect Raspberry Pi 3B directly to LoRa module via SPI through hardware abstraction layer | Gateway receives node heartbeats | Completed - HAL baseline | Codex/User |  | 2026-05-13 | LoRa SPI hardware abstraction added and validated with simulated heartbeat intake. Gateway snapshot now records node heartbeats and rejects wrong-gateway frames. | rpi-gateway/gateway_sim/lora_spi.py; gateway_sim/simulator.py; run_simulation.py --lora-spi-demo; unittest 8 tests passed; compileall passed. | Simulation-safe HAL baseline only. Real Raspberry Pi SPI/SX1278 driver calls and physical wiring verification remain future hardware bring-up work.
5.1 | 5 Router Link | Router-to-Router Link | Configure/verify two WiFi routers connected wirelessly as simulated satellite path | Gateway A can ping Gateway B through router path | Not Started | User |  |  |  | Ping log
5.2 | 5 Router Link | Latency Simulation | Apply 500-700 ms simulated latency using Linux tc/netem where applicable | Latency measured in logs | Not Started | User/Codex |  |  |  | Ping log
6.1 | 6 Failover | Failover State Machine | Implement RSSI < -78 dBm for 10 seconds and ACK/timeout failover triggers | Failover starts within 10 seconds | Not Started | Codex/User |  |  |  | Test log | Use Codex task C5.
6.2 | 6 Failover | Store and Forward | Buffer messages during failover and preserve order | No message loss during route switch | Not Started | Codex/User |  |  |  | Queue logs
6.3 | 6 Failover | Recovery | Return to MANET after stable link for 10 seconds; complete switch within 5 seconds | Recovery passes acceptance criteria | Not Started | Codex/User |  |  |  | Timestamped logs
7.1 | 7 Android | Android Project | Create Android Studio Kotlin app MVP | Project builds | Not Started | Codex/User |  |  |  | Build screenshot | Use Codex task C6.
7.2 | 7 Android | Bluetooth Pairing | Pair Android phone to assigned ESP32 node via Bluetooth | Phone can send test message to node | Not Started | Codex/User |  |  |  | App screenshot/serial log
7.3 | 7 Android | Network Selection | Add Auto, LoRa, WiFi, GSM manual mode selector | UI and internal state work | Not Started | Codex/User |  |  |  | App screenshot
8.1 | 8 Test Campaign | Baseline Test | Run DOCX baseline operation test | PDR >=95%, MANET forms <30 sec, satellite inactive | Not Started | User |  |  |  | Test report
8.2 | 8 Test Campaign | Degradation Test | Run DOCX degradation detection test | RSSI < -78 dBm for 10 seconds detected | Not Started | User |  |  |  | Test report
8.3 | 8 Test Campaign | Failover Test | Run DOCX failover activation test | Failover trigger time = 10 seconds | Not Started | User |  |  |  | Test report
8.4 | 8 Test Campaign | Sustained Operation | Run 24-hour sustained emergency operation test | Uptime >=80%; no unrecoverable failure | Not Started | User |  |  |  | Test report
8.5 | 8 Test Campaign | Recovery Test | Run DOCX recovery/reversion test | Switch back within 5 seconds with no message loss | Not Started | User |  |  |  | Test report
STEP 023 | 23 Integrated ESP32/Android | End-to-End Android-LoRa-Android Messaging | Validate Android Phone A to NODE_A to LoRa to NODE_B to Android Phone B using addressed destination messaging. | Terminal logs show BT_RX, LORA_TX, LORA_RX, LORA_PROTOCOL_RX, and BT_TX_FROM_LORA. | Completed | Codex/User |  | 2026-05-13 | Hardware bridge and demo APK validated. Phone B sent a typed message through NODE_B over LoRa to NODE_A, and Phone A displayed the readable incoming message. | Android demo APK path: android-chat-app/demo-apk/PUP-MANET-Messenger-Step023-Demo-debug.apk; NodeA_Terminal.txt / NodeB_Terminal.txt; phoneA/phoneB screenshots; task log ANDROID_DEMO_APK_MESSAGE_FLOW.md; commit 03d4cb0. | Addressed specific-node demo is ready for client showing. This is not broadcast mode, and GSM remains a later workbook step.
STEP 024 | 24 Gateway | Raspberry Pi Gateway Integration - Simulation Baseline | Create simulation-first gateway baseline before Raspberry Pi hardware integration. | Gateway simulation runs locally and unit tests pass. | Completed | Codex |  | 2026-05-12 | Python gateway simulator and tests created in rpi-gateway. | python3 run_simulation.py; python3 -m unittest discover -s tests; Step 024 task log; commit 6bea5a5. | Hardware SPI/LoRa gateway integration remains later workbook step.

## Hardware BOM
Hardware Bill of Materials and Notes
Item | Qty | Use | Recommended Spec | Already Available? | Priority | Risk | Validation Test | Status | Notes
ESP32 Dev Board | 6+ | MANET nodes | ESP32 WROOM-32 acceptable; ESP32-S3 optional | Yes/confirm | High | Pin/library differences | Blink + serial + LoRa init | Planned | Use same board type if possible.
SX1278 Ra-02 433 MHz | 8 | 6 nodes + 2 gateways | 433 MHz module with correct antenna | Yes/confirm | High | Regulatory/power limits; bad antenna | LoRa send/receive at short range | Planned | Use low power for prototype.
Raspberry Pi 3B | 2 | Gateways | Pi 3B with stable 5V supply | Confirm | High | SPI wiring, CPU limits | Python LoRa gateway receives packets | Planned | Use Lite OS if possible.
WiFi Router 2.4 GHz | 2 | Satellite simulation | Router that supports wireless bridge/repeater/client mode preferred | Yes | High | May not bridge wirelessly | Gateway ping test | Planned | If unsupported, use OpenWrt/travel router.
Android Phone | 1+ | Chat app testing | Android 8+ recommended | Confirm | Medium | Network permissions/background limits | Install APK, connect to gateway | Future | Start web dashboard first.
Li-ion Battery Pack | 6 | Portable nodes | 3.7V/5V boost or regulated 5V | Confirm | Medium | Voltage sag | Runtime and battery reading test | Future | Simulation first.

## Config Tracker
Configuration Tracker
Parameter | Default / Starting Value | Where Used | Reason | Can Change? | Updated Value | Date Updated | Notes
LoRa Frequency | 433 MHz / PH_433-compatible prototype setting | ESP32 + Pi LoRa | Available SX1278 Ra-02 hardware | Yes |  |  | Verify compliance for non-lab use.
LoRa TX Power | Start low; do not maximize during lab tests | ESP32 + Pi LoRa | Reduce interference and stay conservative | Yes |  |  | Document exact dBm after firmware phase.
RSSI Degradation Threshold | -78 dBm | Routing/failover | From project document; conservative quality threshold | Yes |  |  | Not hard LoRa failure threshold.
RSSI Critical Threshold | -95 dBm | Routing/failover | More realistic LoRa degradation marker | Yes |  |  | Tune after field tests.
Failover Delay | 10 seconds | Gateway logic | From project document | Yes |  |  | Trigger after stable failure condition.
Recovery Stable Time | 10 seconds | Gateway logic | Avoid flapping | Yes |  |  | Revert only after stable link.
Satellite Sim Latency | 500-700 ms | Pi tc/netem | Project target | Yes |  |  | Apply on gateway interface.
Max Hop Count | 3 | ESP32 mesh | Small six-node prototype | Yes |  |  | Increase only after testing.
ACK Retry Count | 3 | Messaging protocol | Reliability vs airtime balance | Yes |  |  | Tune after PDR tests.
Destination Not Local Rule | Route to next network via gateway | Gateway logic | User requirement | No |  |  | If destination unknown locally, forward to remote gateway.
Codex/GitHub Configuration Tracker
Item | Recommended Value | Actual Value | Where Set | Owner | Status | Evidence | Notes
GitHub Repository | pup-manet-emergency-messaging |  | GitHub | User | Not Started | Repo URL
Local Repo Path | MacBook Pro local project folder |  | Mac Finder/Terminal | User | Not Started | pwd output
Codex Local Tool | Installed on MacBook Pro M1 Max | Installed | Mac terminal | User | Available | codex --version output | User confirmed installed.
Codex Cloud/GitHub | Connect repo to Codex when ready |  | Codex settings | User | Not Started | Codex environment screenshot/link
AGENTS.md | Root-level project instructions file |  | Repo root | Codex/User | Not Started | Commit hash
Default Branch | main |  | GitHub | User | Not Started | GitHub screenshot
Workbook Location | docs/workbook/PUP_MANET_Implementation_Workbook.xlsx |  | GitHub repo | User | Not Started | Commit hash
Diagrams Location | docs/diagrams/ |  | GitHub repo | User | Not Started | Commit hash

## Packet Protocol
Proposed Packet Protocol
Packet Type | Required Fields | Purpose | ACK Required? | Stored? | Example | ESP32 Role | Gateway Role
HELLO | type,node_id,network_id,battery,rssi_last,snr_last,uptime | Neighbor discovery and health | No | Latest only | HELLO A1 NET_A batt=82 | Broadcast periodically | Update node table
MSG | type,msg_id,src,dst,network_id,payload,ttl,path,timestamp | User text message | Yes | Yes | A1 to B2: emergency text | Forward/receive/ACK | Route local or remote
ACK | type,msg_id,src,dst,status,path,timestamp | Confirm delivery or relay acceptance | No | Yes | ACK for MSG123 | Return to previous hop | Update delivery state
ROUTE_ADV | type,gateway_id,network_id,metric,hop_count | Gateway/route advertisement | No | Latest only | GWA advertises NET_A | Store route score | Advertise network reachability
NACK | type,msg_id,reason,last_hop | Signal failure | No | Yes | Destination unreachable | Try alternate route | Trigger gateway forwarding

## Routing & Failover
Routing & Failover Logic - Test-Aligned
Mode | Trigger | Primary Action | Fallback Action | Required Log Fields | Acceptance Criteria | Development Phase | Status
Baseline | Startup / stable links | 6 nodes discover neighbors and exchange LoRa messages | Keep simulated satellite inactive | startup_time, neighbor_count, pdr, rssi, snr | MANET forms ≤30 sec; PDR ≥95%; satellite inactive | ESP32 + RPi simulation | Pending
Degradation Detection | RSSI < -78 dBm for 10 sec or repeated ACK failure | Mark route degraded; record event | Prepare gateway failover route | rssi_min, snr, ack_fail_count, degrade_start, degrade_end | Degradation detected after 10 sec | ESP32 + RPi simulation | Pending
Failover Activation | Route unavailable or destination not found locally | Gateway forwards via WiFi-router simulated satellite | Use GSM only if explicitly selected/available | failover_start, failover_end, route_used, queue_depth | Failover trigger time = 10 sec | RPi gateway | Pending
Store & Forward | High latency or receiver unavailable | Queue messages and retry until ACK | Preserve FIFO order | message_id, retry_count, queue_time, ack_time | No message loss during recovery test | RPi gateway | Pending
Recovery | MANET route stable for 10 sec | Switch back to primary LoRa route | Deactivate simulated satellite path for normal traffic | recovery_start, recovery_end, route_before, route_after | Switchback ≤5 sec; no message loss | RPi gateway | Pending
Manual App Selection | User selects LoRa / WiFi / GSM | Use selected interface when available | Show unavailable warning if selected path fails | selected_network, actual_network, error | Manual mode must not break Auto mode tests | Android app | Pending

## Simulation Plan
Simulation-First Development Plan
Simulation Item | Description | Output File/Module | Inputs | Expected Output | Pass Criteria | Priority | Status | Notes
Node simulator | Emulates ESP32 node behavior: HELLO, MSG, ACK, retry, battery | sim_node.py | Node ID, network ID, links | Console/log packets | 6 nodes run simultaneously | High | Not Started
Gateway simulator | Emulates Pi gateway and inter-network routing | sim_gateway.py | GWA/GWB config | Routes unknown destinations to other network | A1 to B2 delivery works | High | Not Started
Network fault simulator | Drops packets, lowers RSSI, adds delay | sim_faults.py | Fault profile | Failover/recovery events | Failover at 10s | High | Not Started
Message store | SQLite or JSONL logs for messages and events | messages.db/logs | Packets/events | Traceable delivery status | No duplicate delivered messages | High | Not Started
Dashboard mock | Optional local web view for simulation | Flask app | Sim state | Node and route display | Usable before hardware | Medium | Not Started

## Android App Plan
Android Messaging App Plan - Bluetooth / WiFi / GSM / LoRa
Feature | Purpose | Minimum Requirement | Test Impact | Interface | Phase | Status | Notes
Bluetooth pairing to ESP32 node | Route messages to LoRa when WiFi/GSM are unavailable | Pair one phone to one MANET node; reconnect automatically | Required for end-to-end LoRa validation | Bluetooth Serial/BLE | Android Phase 1 | Pending | Start with classic Bluetooth SPP if ESP32 Android compatibility is acceptable; BLE if needed.
Auto network selection | Select best available route | Check WiFi, GSM, Bluetooth-LoRa status | Supports degraded/failover behavior | Android network APIs + BT status | Android Phase 2 | Pending | Auto should prefer local WiFi when valid, then GSM, then LoRa depending on policy; tests can force LoRa.
Manual route selection | User can choose LoRa, WiFi, or GSM | Dropdown or segmented control | Allows controlled test cases | UI setting | Android Phase 2 | Pending | Manual setting must show selected and actual route.
Message status | Show sent, queued, delivered, failed | Display ACK state and route used | Needed for validation evidence | Gateway/API + BT response | Android Phase 2 | Pending | Keep message IDs visible in debug mode.
Simulation mode | Test without real radios | Mock route status and message delivery | Used before hardware testing | Local mock service | Android Phase 0 | Pending | Important because development starts in simulation.

## Test Campaign
Test Campaign - Pass/Fail Mapping to Updated Diagrams
Test | System Mode | Required Setup | Procedure Focus | Measured Parameters | Acceptance Criteria | Diagram Reference | Workbook Reference | Evidence to Capture | Status
Baseline Operation | Normal LoRa MANET | 6 ESP32 LoRa nodes, 2 gateways, satellite routers inactive | Auto-discovery and periodic text packets | RSSI, SNR, hop count, PDR, latency | PDR ≥95%; MANET forms ≤30 sec; satellite inactive | System Diagram + Data Flow steps 1-4 | Routing & Failover row Baseline | Startup logs, PDR report, screenshot | Pending
Network Degradation Detection | Degraded MANET | Same as baseline with distance/attenuation introduced | Lower RSSI until threshold condition | RSSI trend, detection time, route change | RSSI < -78 dBm for 10 sec must be detected | Control Logic block | Routing & Failover row Degradation Detection | RSSI log graph/table | Pending
Failover Activation | Failover via simulated satellite | MANET active, WiFi router-to-router link available | Route unavailable or destination not found locally | Trigger time, gateway status, queue depth | Failover trigger time = 10 sec | System Diagram failover path; Data Flow step 5 | Routing & Failover row Failover Activation | Gateway logs + message delivery proof | Pending
Sustained Emergency Operation | Emergency operation | Battery-powered nodes and gateways running | Run for 24 hours with controlled events | Uptime, battery, route stability, queue health | Uptime ≥80%; no crash/deadlock | System Diagram test-critical logic | Simulation Plan + Progress Tracker | 24-hour service logs | Pending
Recovery and Reversion | Recovery mode | Start in failover, then restore MANET link quality | Stable RSSI for 10 sec then switch back | Recovery time, packet loss, route before/after | Switchback ≤5 sec; no message loss | Data Flow recovery row | Routing & Failover row Recovery | Route-change logs + message ACKs | Pending

## Progress Tracker
Progress Log
Date | Step ID | What Was Done | Result | Evidence | Updated By | Next Step | Notes
2026-05-12 | STEP 023 | Completed end-to-end Android to LoRa to Android hardware bridge using two Android phones and two ESP32 LoRa nodes. | Completed | NodeA/NodeB terminal logs: BT_RX, LORA_TX BT1 relay, LORA_RX, LORA_PROTOCOL_RX, BT_TX_FROM_LORA; commit 38e7b57. | Codex + User | STEP 024 - Raspberry Pi Gateway Integration | Specific-node messaging validated. Broadcast and GSM remain later workbook work.
2026-05-12 | STEP 024 | Created Raspberry Pi gateway simulation baseline in rpi-gateway with six nodes, two gateways, WiFi-router simulated satellite path, buffering, ACK, failover, and recovery. | Completed - simulation baseline | python3 run_simulation.py succeeded; python3 -m unittest discover -s tests passed 6 tests; compileall succeeded; commit 6bea5a5. | Codex | Next workbook step after Step 024 | No Raspberry Pi SPI/LoRa hardware integration yet; hardware remains later step.
2026-05-13 | STEP 023 DEMO APK | Updated Android demo APK flow and validated physical typed-message demo using two phones, two ESP32 Bluetooth links, and LoRa between NODE_A and NODE_B. | Completed - demo-ready | Phone B -> PUP-MANET-NODE_B -> LoRa -> PUP-MANET-NODE_A -> Phone A showed Incoming: message from Phone b; APK built at android-chat-app/demo-apk/PUP-MANET-Messenger-Step023-Demo-debug.apk; commit 03d4cb0. | Codex + User | Proceed to next workbook step after demo baseline is accepted. | Current demo is addressed node-to-node messaging. Broadcast and GSM network behavior are not implemented yet and remain future workbook scope.
2026-05-13 | 4.2 / STEP 025 | Added Raspberry Pi LoRa SPI hardware abstraction baseline and simulated node heartbeat intake for the gateway layer. | Completed - HAL baseline | python3 run_simulation.py --lora-spi-demo received 2 heartbeats; python3 -m unittest discover -s tests passed 8 tests; python3 -m compileall gateway_sim run_simulation.py passed. | Codex | Next workbook step after LoRa SPI HAL baseline. | No real Raspberry Pi SPI/SX1278 driver calls yet. Hardware wiring verification remains later bring-up scope.

## Issue Log
Issue / Troubleshooting Log
Issue ID | Date | Step ID | Problem | Error / Symptom | Root Cause | Fix Applied | Status | Notes

## Decision Log
Design Decision Log
Decision ID | Date | Decision | Reason | Alternatives Considered | Impact | Status | Notes
D1 | 2026-05-04 | Use simulation-first workflow | User has physical nodes but wants to start with simulation | Hardware-first development | Reduces debugging risk | Accepted
D2 | 2026-05-04 | Start with controlled reliable mesh instead of full AODV | AODV on LoRa ESP32 is complex and hard to debug initially | Full AODV immediately | Faster prototype; can evolve later | Recommended
D3 | 2026-05-04 | If destination is not local, route to next network via gateway | User requirement | Drop unknown destinations | Enables Network A to B messaging | Accepted
D4 | 2026-05-04 | Develop ESP32 code, then Raspberry Pi gateway, then Android app | User requested order | Android first | Ensures app integrates with stable backend | Accepted
2026-05-05 | Development workflow | Use Codex Web + GitHub as primary and Codex CLI on Mac as secondary. VS Code optional only. | User confirmed Codex installed on MacBook Pro M1 Max and wants no VS Code dependency. | Accepted | Marvin/Project | Implementation workbook updated | Proceed to GitHub repo setup

## System Diagram
System Architecture Diagram - Test Procedure Aligned
Updated to prioritize DOCX test procedures: baseline MANET, RSSI degradation detection, failover activation, sustained operation, and recovery.

## Data Flow
Message / Data Flow Diagram - Test Procedure Aligned
Updated to prioritize DOCX test procedures: baseline MANET, RSSI degradation detection, failover activation, sustained operation, and recovery.

## Codex GitHub Workflow
Codex + GitHub Workflow — VS Code Optional
Stage | Tool | Where it runs | Purpose | Input required | Output expected | Who validates | Workbook update required | GitHub action | Pass condition | Notes
0. Baseline repo | GitHub + Codex Web | Browser | Create empty project repository and documentation baseline | Workbook, diagrams, DOCX test requirements | Repo with folders, README, AGENTS.md, docs | User + ChatGPT | Yes: Repo baseline complete | Initial commit | Repo opens and files are visible | No VS Code required
1. Codex instructions | Codex Web | Cloud | Create/verify AGENTS.md so Codex follows workbook and test procedures | Workbook step number and coding rules | AGENTS.md with project rules | User + ChatGPT | Yes: AGENTS.md approved | PR or direct commit | Codex follows scope and does not rewrite unrelated files | Every Codex task must cite workbook step
2. Local Codex CLI setup | Codex CLI | MacBook Pro M1 Max terminal | Allow local repo review and controlled edits without VS Code | GitHub repo cloned locally | Codex CLI can read project and propose edits | User | Yes: CLI setup evidence | Optional local branch commit | codex command runs in repo folder | Used for local checks/troubleshooting
3. ESP32 simulation | Codex Web or CLI | GitHub cloud/local Mac | Create PlatformIO project with simulation mode first | Step prompt + packet format | Compilable ESP32 code with simulated LoRa/messages | User + ChatGPT | Yes: build result and notes | PR | PlatformIO build passes | Hardware not required yet
4. ESP32 LoRa + Bluetooth | Codex Web or CLI | GitHub cloud/local Mac | Add SX1278 LoRa and Android Bluetooth bridge | Pin map, baud, Bluetooth pairing rules | Firmware supports phone-to-LoRa bridge | User hardware test | Yes: test evidence/screenshots | PR | Message sent from Android/serial reaches LoRa packet layer | Physical Bluetooth/LoRa tested by user
5. Raspberry Pi gateway simulation | Codex Web or CLI | Cloud/local Mac | Build Python gateway logic without hardware first | Packet protocol, failover rules | Gateway simulator, web dashboard/logs | User + ChatGPT | Yes: simulation test result | PR | Simulated 6-node traffic passes baseline/degradation/failover | Python tests can run in Codex
6. Raspberry Pi LoRa SPI | Codex Web or CLI | Repo + Raspberry Pi hardware | Add real SX1278 SPI support to gateway | Wiring/pin map | Gateway receives LoRa packets from nodes | User hardware test | Yes: hardware evidence | PR | Pi receives/sends LoRa packet reliably | Physical test cannot be completed by Codex alone
7. Router-to-router simulated satellite | Codex Web or CLI | Raspberry Pi + routers | Implement gateway-to-gateway WiFi path and latency simulation | Router IPs, network settings | Inter-gateway message forwarding | User hardware test | Yes: latency/log evidence | PR | Network A can route message to Network B | Use WiFi routers to simulate satellite path
8. Android app | Codex Web or CLI | GitHub cloud/local Mac | Create Android messaging app | UI requirements, network modes | Android Studio project | User + phone test | Yes: APK/build/test evidence | PR | App builds and can select Auto/WiFi/GSM/LoRa | Android Studio still used for build/run if needed
9. Integrated validation | Codex + User hardware | Physical setup | Run DOCX test campaign | 6 nodes, 2 gateways, 2 routers, phones | Completed test log and workbook evidence | User + ChatGPT | Yes: all test sheets updated | Final PR/Release tag | All acceptance criteria passed | Workbook is final continuation reference

## Codex Task Prompts
Codex Task Prompts — One Task Per Workbook Step
Task ID | Workbook Step | Use With | Prompt Title | Prompt | Expected Output | Allowed Files | Validation | Workbook Update
C0 | 0.1 | Codex Web | Create baseline repo | Create the repository structure for pup-manet-emergency-messaging. Add README.md, AGENTS.md, docs/workbook, docs/diagrams, docs/test-procedures, esp32-node-platformio, rpi-gateway, and android-chat-app folders. Do not implement application code yet. | Baseline repo structure | All top-level docs/folders | Repo opens and README explains workflow | Mark repo baseline complete
C1 | 1.1 | Codex Web | Write AGENTS.md | Create AGENTS.md for this project. Codex must follow the workbook step number, keep ESP32/RPi/Android separate, preserve test procedure alignment, avoid unrelated rewrites, and report validation commands/results. | AGENTS.md | AGENTS.md only unless README reference needed | AGENTS.md includes scope and validation rules | Mark Codex instruction baseline complete
C2 | 2.1 | Codex CLI | Inspect repo locally | Inspect this repository against AGENTS.md and the workbook. Do not modify files. Report missing folders, unclear setup, and recommended next task. | Review report only | No file changes | git status clean after task | Record local CLI inspection
C3 | 3.1 | Codex Web/CLI | ESP32 simulation project | Create the ESP32 PlatformIO project in esp32-node-platformio with simulation mode only. Implement message ID, source, destination, hop count, ACK/retry simulation, and serial logs. Do not add real LoRa hardware code yet. | Compilable PlatformIO project | esp32-node-platformio, README section | PlatformIO build passes | Record build output
C4 | 4.1 | Codex Web/CLI | ESP32 LoRa packet layer | Add SX1278 Ra-02 packet abstraction while preserving simulation mode. Use a hardware interface layer so simulation and physical LoRa can be selected by config. Include RSSI/SNR fields in received packet metadata. | LoRa abstraction + config | esp32-node-platformio | Build passes; simulation still works | Record build/test result
C5 | 4.2 | Codex Web/CLI | Bluetooth bridge | Add Bluetooth serial bridge for Android-to-ESP32 messaging. Preserve existing LoRa/simulation code. Include manual mode support placeholder: AUTO, LORA, WIFI, GSM. | Bluetooth bridge code | esp32-node-platformio | Build passes; serial/Bluetooth message parser test documented | Record Bluetooth test
C6 | 5.1 | Codex Web/CLI | RPi gateway simulator | Create rpi-gateway Python project with simulator for 6 MANET nodes, 2 gateways, and 2 WiFi-router satellite path. Implement routing, message buffer, ACK/retry, failover trigger after 10 seconds, and recovery after 10 seconds. | Python gateway simulator | rpi-gateway | Unit tests/simulation logs pass | Record simulation result
C7 | 8.1 | Codex Web/CLI | Android app skeleton | Create Android app skeleton for messaging. Include screens for chat, node pairing status, and network mode selection: AUTO, WIFI, GSM, LORA. Do not require real Bluetooth/GSM implementation in first task. | Android project skeleton | android-chat-app | Gradle build passes if environment configured | Record build result

## Repo Structure
Repository Structure — Codex/GitHub Source of Truth
Path | Purpose | Owned by | Generated/Edited by Codex | Hardware dependent | Build/Test command | Notes | Status | Last Updated
/README.md | Project overview and workflow | Project | Yes | No | N/A | Explains Codex-only workflow | Planned | 2026-05-05
/AGENTS.md | Codex operating rules | Project | Yes | No | N/A | Must be reviewed before coding | Planned | 2026-05-05
/docs/workbook/ | Workbook tracker | Project | User/ChatGPT | No | N/A | Updated after each completed step | Planned | 2026-05-05
/docs/diagrams/ | System and flow diagrams | Project | User/ChatGPT | No | N/A | Test-aligned diagrams | Planned | 2026-05-05
/docs/test-procedures/ | DOCX-derived validation references | Project | User/ChatGPT | No | N/A | Acceptance criteria live here | Planned | 2026-05-05
/esp32-node-platformio/ | ESP32 LoRa/Bluetooth node firmware | ESP32 | Yes | Yes | pio run | Simulation first, hardware later | Planned | 2026-05-05
/rpi-gateway/ | Raspberry Pi gateway service/dashboard | RPi | Yes | Partly | python -m pytest | Simulation first, SPI later | Planned | 2026-05-05
/android-chat-app/ | Android messaging app | Android | Yes | Partly | ./gradlew build | Manual Auto/WiFi/GSM/LoRa selection | Planned | 2026-05-05

## Codex CLI on Mac
Codex CLI on MacBook Pro M1 Max
Step | Command / Action | Purpose | Expected result | When to use | Workbook evidence | Risk / Warning | Status
1 | Create/clone GitHub repo locally | Prepare local project folder for Codex CLI | Repo folder exists on Mac | Before local Codex tasks | Screenshot or terminal output | Do not create duplicate unrelated folders | Planned
2 | cd pup-manet-emergency-messaging | Enter repo root before running Codex | Terminal path is repo root | Every CLI session | Terminal output | Running Codex outside repo may edit wrong folder | Planned
3 | codex | Start Codex CLI | Interactive Codex session opens | Local review/editing | Screenshot or note | Do not approve large rewrites without review | Planned
4 | Ask Codex to inspect only first | Prevent unnecessary rewrites | Codex reports findings before changing files | Before any coding task | Codex summary | Must keep changes scoped to workbook step | Planned
5 | Run local build/test commands | Verify code before commit/PR | Build/test output available | After Codex changes | Build log | Hardware tests still require actual devices | Planned
6 | git status / git diff | Review changed files | Only expected files changed | Before commit | Diff summary | Never commit secrets or local config | Planned
7 | Commit and push branch | Send work to GitHub | Branch visible in GitHub | After successful review | Commit hash | Use meaningful commit messages | Planned